## Slide 1
Monthly Portfolio Health Review
Professional Services — Client Implementation Portfolio
July 2026 | Prepared for Executive Review

## Slide 2
Portfolio Snapshot
Two active implementations — one Amber, one Red. Neither is Green this month.
Meridian S2P Implementation
PM: Arjun Mehta | Stage: Configuration & Build
AMBER
Composite score: 68.9/100
71% complete
Bottom line:
Ahead on completion %, but critical-path tasks are slipping ~47 days on average — the schedule tag doesn't yet reflect it.
Solvara S2P Implementation
PM: Rohan Kapoor | Stage: Training Phase I
RED
Composite score: 45.5/100
44% complete
Bottom line:
Behind the planned pace (44% done vs 59% of time elapsed) with a Red PM-reported schedule status.
Zycus Professional Services | Confidential
2

## Slide 3
Trend: PM-Reported Status Understates Ground-Level Risk
Across both projects, the task-level data tells a more cautious story than the top-line status field.
Chart: Meridian: task RAG mix (PM status = Green)
| Meridian
Red-tagged tasks | 60
Yellow-tagged tasks | 146
Green-tagged tasks | 121
What the numbers show
Meridian's project-level Schedule Health is reported Green, but 206 of 327 tagged tasks (63%) sit at Yellow or Red, and critical-path tasks are slipping ~47 days on average.
Solvara carries no On Hold tasks or blocker flags at the task level, yet is 15 points behind its planned pace and self-reports Red — the opposite gap direction.
Pattern: top-line RAG fields move on PM judgment calls; task-level signals move independently and sometimes lead them by weeks.
Zycus Professional Services | Confidential
3

## Slide 4
Emerging Risks
Three patterns to watch over the next reporting cycle.
01
Critical-path erosion is invisible at the summary level
Meridian's critical-path tasks are slipping an average of 47 days while the project-level tag stays Green. If uncorrected, this gap surfaces as a missed go-live date with no early warning.
02
Client-side sign-off is the recurring blocker language
Comment text on both projects clusters around "pending," "TBD," and "awaiting sign-off" — almost always attributed to the client side, not Zycus delivery capacity.
03
Solvara's pace deficit is widening without a matching blocker count
44% complete against 59% of elapsed time, with zero flagged blockers — the shortfall looks like scope, resourcing, or engagement pace rather than a single stuck task.
Zycus Professional Services | Confidential
4

## Slide 5
Recommendations
Where executive attention will have the most leverage this month.
01
Require critical-path variance, not just the summary tag, in weekly PM reporting
Closes the Green-status / Red-reality gap seen on Meridian before it becomes a date slip.
02
Escalate outstanding client sign-offs directly with Solvara and Meridian sponsors
Both projects' blockers trace back to client-side approvals — a sponsor-level nudge outperforms PM-level follow-up.
03
Reset Solvara's delivery pace conversation this week
A 15-point pace deficit with no active blockers points to a capacity or scope conversation, not a task fix.
Zycus Professional Services | Confidential
5

## Slide 6
Next Steps
01
This report regenerates automatically each week directly from the live project plans — no manual chasing required.
02
Executive sponsors receive the Meridian critical-path variance and Solvara pace numbers ahead of next steering call.
03
Escalation owners follow up on outstanding client sign-offs within 5 business days.
Prepared by the Project Health Reporting Agent | Professional Services