## Project Plan
No.of days Until Today | No.of days | Target start date to Today | Project Name | Project Category | Ancestors | Project Manager | Phase/Milestone | Area | At Risk? | Schedule Health | Task Name | Status | % Complete | Start Date | End Date | Priority | Owner | On Hold? | Not Applicable? | Duration | Predecessors | Total Float | Critical ? | Baseline Start | Baseline Finish | Variance | Status Comment | Baseline Start Date | Baseline End Date | Comments | Assigned To | Start | Finish | Baseline Start2 | Baseline Finish2 | Variance2
#UNPARSEABLE | #UNPARSEABLE | #UNPARSEABLE |  | #UNPARSEABLE | 0 | Rohan Kapoor |  |  |  | Red | Zycus - Solvara S2P Implementation | In Progress | 44% | 2026-02-11 | 2026-10-09 |  |  |  |  | 170d |  | 0 |  | 2026-05-03 | 2026-05-20 | -2d | [7 empty] | 2026-02-11 | 2026-09-29 | -8d
#UNPARSEABLE | #UNPARSEABLE | #UNPARSEABLE |  | #UNPARSEABLE | 1 | Rohan Kapoor |  |  |  | Green | Contract Sign Off | Completed | 100% | 2026-02-11 | 2026-02-11 |  |  |  |  | 1d |  | 169 | [11 empty] | 2026-02-11 | 2026-02-11 | 0
#UNPARSEABLE | #UNPARSEABLE | #UNPARSEABLE |  | #UNPARSEABLE | 2 | Rohan Kapoor |  |  |  | Green | Contract signing between Solvara and Zycus | Completed | 100% | 2026-02-11 | 2026-02-11 |  |  |  |  | 1d |  | 0 | TRUE | [7 empty] | Solvara Project Sponsor, Zycus Sales |  |  | 2026-02-11 | 2026-02-11 | 0
#UNPARSEABLE | #UNPARSEABLE | #UNPARSEABLE |  | #UNPARSEABLE | 2 | Rohan Kapoor |  |  |  | Green | Contract Sign Off | Completed | 100% | 2026-02-11 | 2026-02-11 |  |  |  |  | 0 | 3 | 169 | [11 empty] | 2026-02-11 | 2026-02-11 | 0
#UNPARSEABLE | #UNPARSEABLE | #UNPARSEABLE |  | #UNPARSEABLE | 1 | Rohan Kapoor |  |  |  | Green | Project Initiation and Data Gathering | Completed | 100% | 2026-02-19 | 2026-03-17 |  |  |  |  | 18d |  | 146 | [11 empty] | 2026-02-12 | 2026-03-18 | 1d
#UNPARSEABLE | #UNPARSEABLE | #UNPARSEABLE |  | #UNPARSEABLE | 2 | Rohan Kapoor |  |  |  | Green | Project Kick Off | Completed | 100% | 2026-02-19 | 2026-03-10 |  |  |  |  | 13d |  | 151 | [11 empty] | 2026-02-12 | 2026-03-18 | 6d
#UNPARSEABLE | #UNPARSEABLE | #UNPARSEABLE |  | #UNPARSEABLE | 3 | Rohan Kapoor |  |  |  | Green | Review Contract Scope | Completed | 100% | 2026-02-23 | 2026-02-23 |  |  |  |  | 1d | 3FS +7d | 158 | [8 empty] | Zycus Project Resources Manager |  |  | 2026-02-23 | 2026-02-23 | 0
#UNPARSEABLE | #UNPARSEABLE | #UNPARSEABLE |  | #UNPARSEABLE | 3 | Rohan Kapoor |  |  |  | Green | Assign Project Team and Internal communication | Completed | 100% | 2026-02-23 | 2026-02-23 |  |  |  |  | 1d | 3FS +7d | 0 | TRUE | [7 empty] | Zycus Project Resources Manager |  |  | 2026-02-23 | 2026-02-23 | 0
#UNPARSEABLE | #UNPARSEABLE | #UNPARSEABLE |  | #UNPARSEABLE | 3 | Rohan Kapoor |  |  |  | Green | Zycus Project Team mobilization and Team alignment | Completed | 100% | 2026-02-19 | 2026-02-23 |  |  |  |  | 3d | 8FF | 0 | TRUE | [7 empty] | Zycus Project Resources Manager |  |  | 2026-02-19 | 2026-02-23 | 0
#UNPARSEABLE | #UNPARSEABLE | #UNPARSEABLE |  | #UNPARSEABLE | 3 | Rohan Kapoor |  |  |  | Green | Setup Project [Server, Email alias, Internal Applications, Central Drive, Internal ticket for STAGING Set Up] | Completed | 100% | 2026-02-24 | 2026-03-05 |  |  |  |  | 7d | 9 | 0 | TRUE | [7 empty] | Zycus Project Team |  |  | 2026-02-24 | 2026-03-05 | 0
#UNPARSEABLE | #UNPARSEABLE | #UNPARSEABLE |  | #UNPARSEABLE | 3 | Rohan Kapoor |  |  |  | Green | Sales / PreSales / Pilots handover | Completed | 100% | 2026-02-24 | 2026-02-25 |  |  |  |  | 2d | 7 | 158 | [8 empty] | Zycus Project Manager, Zycus Project Team, Zycus Sales |  |  | 2026-02-24 | 2026-02-25 | 0
#UNPARSEABLE | #UNPARSEABLE | #UNPARSEABLE |  | #UNPARSEABLE | 3 | Rohan Kapoor |  |  |  | Green | Pre-kick off meeting with internal stakeholders | Completed | 100% | 2026-02-26 | 2026-02-26 |  |  |  |  | 1d | 11 | 158 | [8 empty] | Zycus Project Manager, Zycus Project Team, Zycus Sales |  |  | 2026-02-26 | 2026-02-26 | 0
#UNPARSEABLE | #UNPARSEABLE | #UNPARSEABLE |  | #UNPARSEABLE | 3 | Rohan Kapoor |  |  |  | Green | Finalize kick off meeting schedule | Completed | 100% | 2026-02-23 | 2026-02-23 |  |  |  |  | 1d |  | 157 | [8 empty] | Solvara Project Manager, Solvara Project Sponsor, Zycus Sales |  |  | 2026-03-02 | 2026-03-02 | 5d
#UNPARSEABLE | #UNPARSEABLE | #UNPARSEABLE |  | #UNPARSEABLE | 3 | Rohan Kapoor |  |  |  | Green | Review SOW with Solvara | Completed | 100% | 2026-02-24 | 2026-02-24 |  |  |  |  | 1d |  | 160 | [8 empty] | Solvara Project Sponsor, Zycus Project Manager |  |  | 2026-02-12 | 2026-02-12 | -8d
#UNPARSEABLE | #UNPARSEABLE | #UNPARSEABLE |  | #UNPARSEABLE | 3 | Rohan Kapoor |  |  |  | Green | Kick off meeting [Introduction Meeting] | Completed | 100% | 2026-02-24 | 2026-02-24 |  |  |  |  | 1d | 13 | 157 | [8 empty] | Solvara Core Project Team, Solvara Project Manager, Zycus Consultant, Zycus Product Specialist, Zycus Project Manager, Zycus Project Team |  |  | 2026-03-03 | 2026-03-05 | 6d
#UNPARSEABLE | #UNPARSEABLE | #UNPARSEABLE |  | #UNPARSEABLE | 3 | Rohan Kapoor |  |  |  | Green | Share Product specific templates [Questionnaire, User Details template, Legacy Data Upload] with Solvara | Completed | 100% | 2026-02-25 | 2026-02-25 |  |  |  |  | 1d | 15 | 157 | [8 empty] | Zycus Product Specialist, Zycus Project Manager |  |  | 2026-03-06 | 2026-03-06 | 6d
#UNPARSEABLE | #UNPARSEABLE | #UNPARSEABLE |  | #UNPARSEABLE | 3 | Rohan Kapoor |  |  |  | Green | Setup Value Introduction kick-off call | Completed | 100% | 2026-03-09 | 2026-03-10 |  |  |  |  | 2d | 16FS +6d | 151 | [8 empty] | Solvara Project Group, Zycus Product Specialist, Zycus Project Manager |  |  | 2026-03-17 | 2026-03-18 | 6d
#UNPARSEABLE | #UNPARSEABLE | #UNPARSEABLE |  | #UNPARSEABLE | 2 | Rohan Kapoor |  |  |  | Green | Zycus Project Set-Up | Completed | 100% | 2026-03-05 | 2026-03-05 |  |  |  |  | 0 | 10 | 154 | [11 empty] | 2026-03-05 | 2026-03-05 | 0
#UNPARSEABLE | #UNPARSEABLE | #UNPARSEABLE |  | #UNPARSEABLE | 2 | Rohan Kapoor |  |  |  | Green | Kick-off Meeting | Completed | 100% | 2026-02-24 | 2026-02-24 |  |  |  |  | 0 | 15 | 160 | [11 empty] | 2026-03-05 | 2026-03-05 | 6d
#UNPARSEABLE | #UNPARSEABLE | #UNPARSEABLE |  | #UNPARSEABLE | 2 | Rohan Kapoor |  |  |  | Green | Implementation Questionnaire and Staging Setup | Completed | 100% | 2026-03-06 | 2026-03-17 |  |  |  |  | 8d |  | 146 | [11 empty] | 2026-03-06 | 2026-03-17 | 0
#UNPARSEABLE | #UNPARSEABLE | #UNPARSEABLE |  | #UNPARSEABLE | 3 | Rohan Kapoor |  |  |  | Green | STAGING Set Up | Completed | 100% | 2026-03-06 | 2026-03-13 |  |  |  |  | 6d |  | 148 | [11 empty] | 2026-03-06 | 2026-03-13 | 0
#UNPARSEABLE | #UNPARSEABLE | #UNPARSEABLE |  | #UNPARSEABLE | 4 | Rohan Kapoor |  |  |  | Green | Company creation on Zycus STAGING environment | Completed | 100% | 2026-03-06 | 2026-03-09 |  |  |  |  | 2d | 10 | 0 | TRUE | [7 empty] | Zycus Product Specialist |  |  | 2026-03-06 | 2026-03-09 | 0
#UNPARSEABLE | #UNPARSEABLE | #UNPARSEABLE |  | #UNPARSEABLE | 4 | Rohan Kapoor |  |  |  | Green | NFR (Non-Functional Requirement) Finalization and sign-off | Completed | 100% | 2026-03-06 | 2026-03-06 |  |  |  |  | 1d | 10 | 153 | [8 empty] | Solvara Core Project Team, Zycus Project Team |  |  | 2026-03-06 | 2026-03-06 | 0
#UNPARSEABLE | #UNPARSEABLE | #UNPARSEABLE |  | #UNPARSEABLE | 4 | Rohan Kapoor |  |  |  | Green | Configure staging setup with base configuration | Completed | 100% | 2026-03-10 | 2026-03-12 |  |  |  |  | 3d | 22 | 0 | TRUE | [7 empty] | Zycus Product Specialist |  |  | 2026-03-10 | 2026-03-12 | 0
#UNPARSEABLE | #UNPARSEABLE | #UNPARSEABLE |  | #UNPARSEABLE | 4 | Rohan Kapoor |  |  |  | Green | Value Definition Discussion | Completed | 100% | 2026-03-10 | 2026-03-11 |  |  |  |  | 2d | 22 | 147 | [8 empty] | Solvara Project Group, Zycus Product Specialist, Zycus Project Manager |  |  | 2026-03-10 | 2026-03-11 | 0
#UNPARSEABLE | #UNPARSEABLE | #UNPARSEABLE |  | #UNPARSEABLE | 4 | Rohan Kapoor |  |  |  | Green | Value Definition Review and Follow-up | Completed | 100% | 2026-03-12 | 2026-03-13 |  |  |  |  | 2d | 25 | 147 | [8 empty] | Solvara Project Group, Zycus Product Specialist, Zycus Project Manager |  |  | 2026-03-12 | 2026-03-13 | 0
#UNPARSEABLE | #UNPARSEABLE | #UNPARSEABLE |  | #UNPARSEABLE | 4 | Rohan Kapoor |  |  |  | Green | Value Definition Sign-off | Completed | 100% | 2026-03-13 | 2026-03-13 |  |  |  |  | 0 | 26 | 147 | [8 empty] | Solvara Project Group, Zycus Product Specialist, Zycus Project Manager |  |  | 2026-03-13 | 2026-03-13 | 0
#UNPARSEABLE | #UNPARSEABLE | #UNPARSEABLE |  | #UNPARSEABLE | 3 | Rohan Kapoor |  |  |  | Green | Quality Reviews | Completed | 100% | 2026-03-13 | 2026-03-17 |  |  |  |  | 3d |  | 146 | [11 empty] | 2026-03-13 | 2026-03-17 | 0
#UNPARSEABLE | #UNPARSEABLE | #UNPARSEABLE |  | #UNPARSEABLE | 4 | Rohan Kapoor |  |  |  | Green | Schedule quality toll | Completed | 100% | 2026-03-13 | 2026-03-13 |  |  |  |  | 1d | 24 | 123 | [8 empty] | Zycus Product Specialist |  |  | 2026-03-13 | 2026-03-13 | 0
#UNPARSEABLE | #UNPARSEABLE | #UNPARSEABLE |  | #UNPARSEABLE | 4 | Rohan Kapoor |  |  |  | Green | Perform quality checks, PSRs as per quality checklist and submit to QC team | Completed | 100% | 2026-03-16 | 2026-03-16 |  |  |  |  | 1d | 29 | 123 | [8 empty] | Zycus Product Specialist |  |  | 2026-03-16 | 2026-03-16 | 0
#UNPARSEABLE | #UNPARSEABLE | #UNPARSEABLE |  | #UNPARSEABLE | 4 | Rohan Kapoor |  |  |  | Green | Quality Check by Zycus QC team | Completed | 100% | 2026-03-17 | 2026-03-17 |  |  |  |  | 1d | 30 | 123 | [8 empty] | Zycus Quality Team |  |  | 2026-03-17 | 2026-03-17 | 0
#UNPARSEABLE | #UNPARSEABLE | #UNPARSEABLE |  | #UNPARSEABLE | 2 | Rohan Kapoor |  |  |  | Green | Implementation Questionnaire and Staging Setup | Completed | 100% | 2026-03-17 | 2026-03-17 |  |  |  |  | 0 | 31 | 123 | [11 empty] | 2026-03-17 | 2026-03-17 | 0
#UNPARSEABLE | #UNPARSEABLE | #UNPARSEABLE |  | #UNPARSEABLE | 1 | Rohan Kapoor |  |  |  | Green | Configuration Validation & Documentation | Completed | 100% | 2026-03-13 | 2026-04-27 |  |  |  |  | 32d |  | 117 | [11 empty] | 2026-03-13 | 2026-04-28 | 1d
#UNPARSEABLE | #UNPARSEABLE | #UNPARSEABLE |  | #UNPARSEABLE | 2 | Rohan Kapoor |  |  |  | Green | Requirement Workshop | Completed | 100% | 2026-03-13 | 2026-04-27 |  |  |  |  | 32d |  | 117 | [11 empty] | 2026-03-13 | 2026-04-27 | 0
#UNPARSEABLE | #UNPARSEABLE | #UNPARSEABLE |  | #UNPARSEABLE | 3 | Rohan Kapoor |  |  |  | Green | CLM Configuration Documentation Workshop | Completed | 100% | 2026-03-13 | 2026-04-17 |  |  |  |  | 26d | 24 | 0 | TRUE | [7 empty] | Solvara Project Team, Solvara SME, Zycus Project Team |  |  | 2026-03-13 | 2026-04-17 | 0
#UNPARSEABLE | #UNPARSEABLE | #UNPARSEABLE |  | #UNPARSEABLE | 3 | Rohan Kapoor |  |  |  | Green | iSupplier Configuration Documentation Workshop | Completed | 100% | 2026-03-13 | 2026-04-15 |  |  |  |  | 24d | 24 | 4 | [8 empty] | Solvara Project Team, Solvara SME, Zycus Project Team |  |  | 2026-03-13 | 2026-04-15 | 0
#UNPARSEABLE | #UNPARSEABLE | #UNPARSEABLE |  | #UNPARSEABLE | 3 | Rohan Kapoor |  |  |  | Green | Integration Configuration Documentation Workshop | Completed | 100% | 2026-04-24 | 2026-04-27 |  |  |  |  | 2d | #REF, #REF | 117 | [8 empty] | Solvara Project Team, Solvara SME, Zycus Project Team |  |  | 2026-04-24 | 2026-04-27 | 0
#UNPARSEABLE | #UNPARSEABLE | #UNPARSEABLE |  | #UNPARSEABLE | 2 | Rohan Kapoor |  |  |  | Green | Configuration Documentation | Completed | 100% | 2026-03-16 | 2026-04-22 |  |  |  |  | 28d |  | 120 | [11 empty] | 2026-04-16 | 2026-04-28 | 4d
#UNPARSEABLE | #UNPARSEABLE | #UNPARSEABLE |  | #UNPARSEABLE | 3 | Rohan Kapoor |  |  |  | Green | iContract Documentation with Merlin | Completed | 100% | 2026-04-20 | 2026-04-20 |  |  |  |  | 1d | 35 | 0 | TRUE | [7 empty] | Solvara Core Project Team, Solvara Project Manager, Zycus Merlin Product Team, Zycus Project Manager, Zycus Project Team |  |  | 2026-04-20 | 2026-04-20 | 0
#UNPARSEABLE | #UNPARSEABLE | #UNPARSEABLE |  | #UNPARSEABLE | 3 | Rohan Kapoor |  |  |  | Green | iSupplier Configuration Documentation | Completed | 100% | 2026-04-16 | 2026-04-16 |  |  |  |  | 1d | 36 | 4 | [8 empty] | Solvara Core Project Team, Solvara Project Manager, Zycus Merlin Product Team, Zycus Project Manager, Zycus Project Team |  |  | 2026-04-16 | 2026-04-16 | 0
#UNPARSEABLE | #UNPARSEABLE | #UNPARSEABLE |  | #UNPARSEABLE | 3 | Rohan Kapoor |  |  |  | Green | IAD Review for iSupplier and iContract | Completed | 100% | 2026-04-21 | 2026-04-21 |  |  |  |  | 1d | 39, 40 | 0 | TRUE | [7 empty] | Solvara Project Manager |  |  | 2026-04-21 | 2026-04-21 | 0
#UNPARSEABLE | #UNPARSEABLE | #UNPARSEABLE |  | #UNPARSEABLE | 3 | Rohan Kapoor |  |  |  | Green | Solvara to review and Sign-off IAD Draft- iSupplier and iContract | Completed | 100% | 2026-04-22 | 2026-04-22 |  |  |  |  | 1d | 41 | 0 | TRUE | [10 empty] | 2026-04-22 | 2026-04-22 | 0
#UNPARSEABLE | #UNPARSEABLE | #UNPARSEABLE |  | #UNPARSEABLE | 3 | Rohan Kapoor |  |  |  | Green | Value Realization Target Discussion | Completed | 100% | 2026-03-16 | 2026-03-16 |  |  |  |  | 1d | 27, #REF | 147 | [8 empty] | Solvara Project Group, Zycus Product Specialist, Zycus Project Manager |  |  | 2026-04-28 | 2026-04-28 | 31d
#UNPARSEABLE | #UNPARSEABLE | #UNPARSEABLE |  | #UNPARSEABLE | 2 | Rohan Kapoor |  |  |  | Green | Configuration Documentation concluded | Completed | 100% | 2026-04-22 | 2026-04-22 |  |  |  |  | 0 | 38 | 120 | [11 empty] | 2026-04-28 | 2026-04-28 | 4d
#UNPARSEABLE | #UNPARSEABLE | #UNPARSEABLE |  | #UNPARSEABLE | 2 | Rohan Kapoor |  |  |  | Green | First draft IAD Sign-off | Completed | 100% | 2026-04-22 | 2026-04-22 |  |  |  |  | 0 | 42 | 120 | [11 empty] | 2026-04-22 | 2026-04-22 | 0
#UNPARSEABLE | #UNPARSEABLE | #UNPARSEABLE |  | #UNPARSEABLE | 1 | Rohan Kapoor |  |  |  | Green | Single Sign On and User details Integration | Completed | 100% | 2026-03-13 | 2026-04-16 |  |  |  |  | 25d |  | 124 | [11 empty] | 2026-03-13 | 2026-04-16 | 0
#UNPARSEABLE | #UNPARSEABLE | #UNPARSEABLE |  | #UNPARSEABLE | 2 | Rohan Kapoor |  |  |  | Green | Single Sign On - SSO | Completed | 100% | 2026-03-13 | 2026-04-16 |  |  |  |  | 25d |  | 124 | [11 empty] | 2026-03-13 | 2026-04-16 | 0
#UNPARSEABLE | #UNPARSEABLE | #UNPARSEABLE |  | #UNPARSEABLE | 3 | Rohan Kapoor |  |  |  | Green | Availability of Technical Team from Customer | Completed | 100% | 2026-03-13 | 2026-03-13 |  |  |  |  | 1d | 24 | 123 | [8 empty] | Solvara Project Manager |  |  | 2026-03-13 | 2026-03-13 | 0
#UNPARSEABLE | #UNPARSEABLE | #UNPARSEABLE |  | #UNPARSEABLE | 3 | Rohan Kapoor |  |  |  | Green | Design and Analysis | Completed | 100% | 2026-03-18 | 2026-04-10 |  |  |  |  | 18d |  | 128 | [11 empty] | 2026-03-18 | 2026-04-10 | 0
#UNPARSEABLE | #UNPARSEABLE | #UNPARSEABLE |  | #UNPARSEABLE | 4 | Rohan Kapoor |  |  |  | Green | Zycus to share Process flow of SSO integration | Completed | 100% | 2026-03-18 | 2026-03-18 |  |  |  |  | 1d | 48, 32 | 123 | [8 empty] | Zycus SSO Team |  |  | 2026-03-18 | 2026-03-18 | 0
#UNPARSEABLE | #UNPARSEABLE | #UNPARSEABLE |  | #UNPARSEABLE | 4 | Rohan Kapoor |  |  |  | Green | Exchange of configuration files | Completed | 100% | 2026-03-19 | 2026-03-19 |  |  |  |  | 1d | 50 | 144 | [8 empty] | Solvara IT Team, Zycus SSO Team |  |  | 2026-03-19 | 2026-03-19 | 0
#UNPARSEABLE | #UNPARSEABLE | #UNPARSEABLE |  | #UNPARSEABLE | 4 | Rohan Kapoor |  |  |  | Green | Exchange of certificates to be used | Completed | 100% | 2026-03-19 | 2026-04-10 |  |  |  |  | 17d | 50 | 128 | [8 empty] | Solvara IT Team, Zycus SSO Team |  |  | 2026-03-19 | 2026-04-10 | 0
#UNPARSEABLE | #UNPARSEABLE | #UNPARSEABLE |  | #UNPARSEABLE | 4 | Rohan Kapoor |  |  |  | Green | Approach to be used for Single Sign On [Claims/Email Address etc.] | Completed | 100% | 2026-03-19 | 2026-04-10 |  |  |  |  | 17d | 50 | 123 | [8 empty] | Solvara IT Team, Zycus SSO Team |  |  | 2026-03-19 | 2026-04-10 | 0
#UNPARSEABLE | #UNPARSEABLE | #UNPARSEABLE |  | #UNPARSEABLE | 3 | Rohan Kapoor |  |  |  | Green | Configuration and Review | Completed | 100% | 2026-04-13 | 2026-04-16 |  |  |  |  | 4d |  | 124 | [11 empty] | 2026-04-13 | 2026-04-16 | 0
#UNPARSEABLE | #UNPARSEABLE | #UNPARSEABLE |  | #UNPARSEABLE | 4 | Rohan Kapoor |  |  |  | Green | Development [STAGING] Environment | Completed | 100% | 2026-04-13 | 2026-04-16 |  |  |  |  | 4d |  | 124 | [11 empty] | 2026-04-13 | 2026-04-16 | 0
#UNPARSEABLE | #UNPARSEABLE | #UNPARSEABLE |  | #UNPARSEABLE | 5 | Rohan Kapoor |  |  |  | Green | Registration of Service Provider URL for client | Completed | 100% | 2026-04-13 | 2026-04-13 |  |  |  |  | 1d | 53 | 127 | [8 empty] | Zycus SSO Team |  |  | 2026-04-13 | 2026-04-13 | 0
#UNPARSEABLE | #UNPARSEABLE | #UNPARSEABLE |  | #UNPARSEABLE | 5 | Rohan Kapoor |  |  |  | Green | Registration TMS URL specific to client | Completed | 100% | 2026-04-13 | 2026-04-13 |  |  |  |  | 1d | 53 | 123 | [8 empty] | Zycus SSO Team |  |  | 2026-04-13 | 2026-04-13 | 0
#UNPARSEABLE | #UNPARSEABLE | #UNPARSEABLE |  | #UNPARSEABLE | 5 | Rohan Kapoor |  |  |  | Green | Configuration of Web Server for service Provider application | Completed | 100% | 2026-04-14 | 2026-04-14 |  |  |  |  | 1d | 57 | 126 | [8 empty] | Zycus SSO Team |  |  | 2026-04-14 | 2026-04-14 | 0
#UNPARSEABLE | #UNPARSEABLE | #UNPARSEABLE |  | #UNPARSEABLE | 5 | Rohan Kapoor |  |  |  | Green | Service Provider application deployment for client and sanity of the deployed setup | Completed | 100% | 2026-04-14 | 2026-04-14 |  |  |  |  | 1d | 57 | 126 | [8 empty] | Zycus SSO Team |  |  | 2026-04-14 | 2026-04-14 | 0
#UNPARSEABLE | #UNPARSEABLE | #UNPARSEABLE |  | #UNPARSEABLE | 5 | Rohan Kapoor |  |  |  | Green | Configuration of Service Provider setup using below mentioned files | Completed | 100% | 2026-04-14 | 2026-04-14 |  |  |  |  | 1d | 57 | 123 | [8 empty] | Zycus SSO Team |  |  | 2026-04-14 | 2026-04-14 | 0
#UNPARSEABLE | #UNPARSEABLE | #UNPARSEABLE |  | #UNPARSEABLE | 5 | Rohan Kapoor |  |  |  | Green | Issue Resolution, if any | Completed | 100% | 2026-04-15 | 2026-04-16 |  |  |  |  | 2d | 60 | 123 | [8 empty] | Zycus SSO Team |  |  | 2026-04-15 | 2026-04-16 | 0
#UNPARSEABLE | #UNPARSEABLE | #UNPARSEABLE |  | #UNPARSEABLE | 5 | Rohan Kapoor |  |  |  | Green | Sign off of SSO on STAGING Environment | Completed | 100% | 2026-04-16 | 2026-04-16 |  |  |  |  | 1d | 61FF | 124 | [8 empty] | Solvara IT Team |  |  | 2026-04-16 | 2026-04-16 | 0
#UNPARSEABLE | #UNPARSEABLE | #UNPARSEABLE |  | #UNPARSEABLE | 2 | Rohan Kapoor |  |  |  | Green | SSO: Completion of Design & Analysis | Completed | 100% | 2026-04-10 | 2026-04-10 |  |  |  |  | 0 | 49 | 128 | [11 empty] | 2026-04-10 | 2026-04-10 | 0
#UNPARSEABLE | #UNPARSEABLE | #UNPARSEABLE |  | #UNPARSEABLE | 2 | Rohan Kapoor |  |  |  | Green | SSO: Completion of Development and Testing | Completed | 100% | 2026-04-16 | 2026-04-16 |  |  |  |  | 0 | 62 | 124 | [11 empty] | 2026-04-16 | 2026-04-16 | 0
#UNPARSEABLE | #UNPARSEABLE | #UNPARSEABLE |  | #UNPARSEABLE | 1 | Rohan Kapoor |  |  |  | Green | Contract Management with Basic Setup | Completed | 100% | 2026-04-23 | 2026-05-05 |  |  |  |  | 8d |  | 112 | [11 empty] | 2026-04-23 | 2026-05-05 | 0
#UNPARSEABLE | #UNPARSEABLE | #UNPARSEABLE |  | #UNPARSEABLE | 2 | Rohan Kapoor |  |  |  | Green | iContract Deployment (Repository + Authoring) | Completed | 100% | 2026-04-23 | 2026-05-05 |  |  |  |  | 8d |  | 112 | [11 empty] | 2026-04-23 | 2026-05-05 | 0
#UNPARSEABLE | #UNPARSEABLE | #UNPARSEABLE |  | #UNPARSEABLE | 3 | Rohan Kapoor |  |  |  | Green | Functional Configuration on STAGING set Up | Completed | 100% | 2026-04-23 | 2026-05-05 |  |  |  |  | 8d |  | 112 | [11 empty] | 2026-04-23 | 2026-05-05 | 0
#UNPARSEABLE | #UNPARSEABLE | #UNPARSEABLE |  | #UNPARSEABLE | 4 | Rohan Kapoor |  |  |  | Green | User Role Configuration | Completed | 100% | 2026-04-23 | 2026-04-23 |  |  |  |  | 1d | 42 | 4 | [8 empty] | Zycus Product Specialist |  |  | 2026-04-23 | 2026-04-23 | 0
#UNPARSEABLE | #UNPARSEABLE | #UNPARSEABLE |  | #UNPARSEABLE | 4 | Rohan Kapoor |  |  |  | Green | Admin Settings Configuration | Completed | 100% | 2026-04-24 | 2026-04-24 |  |  |  |  | 1d | 68 | 118 | [8 empty] | Zycus Product Specialist |  |  | 2026-04-24 | 2026-04-24 | 0
#UNPARSEABLE | #UNPARSEABLE | #UNPARSEABLE |  | #UNPARSEABLE | 4 | Rohan Kapoor |  |  |  | Green | Readiness for Pre-UAT | Completed | 100% | 2026-04-24 | 2026-04-24 |  |  |  |  | 1d | 68 | 4 | [8 empty] | Zycus Product Specialist |  |  | 2026-04-24 | 2026-04-24 | 0
#UNPARSEABLE | #UNPARSEABLE | #UNPARSEABLE |  | #UNPARSEABLE | 4 | Rohan Kapoor |  |  |  | Green | Pre-UAT | Completed | 100% | 2026-04-27 | 2026-05-05 |  |  |  |  | 6d |  | 112 | [11 empty] | 2026-04-27 | 2026-05-05 | 0
#UNPARSEABLE | #UNPARSEABLE | #UNPARSEABLE |  | #UNPARSEABLE | 5 | Rohan Kapoor |  |  |  | Green | Pre-UAT - Provide End to end walkthrough of configured iContract to Solvara | Completed | 100% | 2026-04-27 | 2026-04-28 |  |  |  |  | 2d | 70 | 4 | [8 empty] | Solvara Core Project Team, Zycus Consultant, Zycus Product Specialist |  |  | 2026-04-27 | 2026-04-28 | 0
#UNPARSEABLE | #UNPARSEABLE | #UNPARSEABLE |  | #UNPARSEABLE | 5 | Rohan Kapoor |  |  |  | Green | Provide feedback - if any for iContract configuration | Completed | 100% | 2026-04-29 | 2026-04-30 |  |  |  |  | 2d | 72 | 4 | [8 empty] | Solvara Project Team |  |  | 2026-04-29 | 2026-04-30 | 0
#UNPARSEABLE | #UNPARSEABLE | #UNPARSEABLE |  | #UNPARSEABLE | 5 | Rohan Kapoor |  |  |  | Green | Zycus to incorporate feedback - as applicable and share final version of Implementation Approach Document [IAD] | Completed | 100% | 2026-04-30 | 2026-05-04 |  |  |  |  | 2d | 73SS +1d | 4 | [8 empty] | Zycus Consultant, Zycus Product Specialist |  |  | 2026-04-30 | 2026-05-04 | 0
#UNPARSEABLE | #UNPARSEABLE | #UNPARSEABLE |  | #UNPARSEABLE | 5 | Rohan Kapoor |  |  |  | Green | Sign off on Pre-UAT and final version of IAD sign off | Completed | 100% | 2026-05-04 | 2026-05-04 |  |  |  |  | 0 | 74 | 4 | [8 empty] | Solvara Project Manager |  |  | 2026-05-04 | 2026-05-04 | 0
#UNPARSEABLE | #UNPARSEABLE | #UNPARSEABLE |  | #UNPARSEABLE | 5 | Rohan Kapoor |  |  |  | Green | WordConnect Installation at Solvara's end | Completed | 100% | 2026-05-04 | 2026-05-05 |  |  |  |  | 2d | 73SS +2d | 112 | [8 empty] | Solvara IT Team, Solvara Project Manager |  |  | 2026-05-04 | 2026-05-05 | 0
#UNPARSEABLE | #UNPARSEABLE | #UNPARSEABLE |  | #UNPARSEABLE | 2 | Rohan Kapoor |  |  |  | Green | iContract: Conclude Functional Configuration | Completed | 100% | 2026-05-04 | 2026-05-04 |  |  |  |  | 0 | 75 | 113 | [11 empty] | 2026-05-04 | 2026-05-04 | 0
#UNPARSEABLE | #UNPARSEABLE | #UNPARSEABLE |  | #UNPARSEABLE | 1 | Rohan Kapoor |  |  |  | Green | Supplier Information Management with Integration | Completed | 100% | 2026-04-23 | 2026-05-15 |  |  |  |  | 16d |  | 104 | [11 empty] | 2026-04-23 | 2026-05-20 | 3d
#UNPARSEABLE | #UNPARSEABLE | #UNPARSEABLE |  | #UNPARSEABLE | 2 | Rohan Kapoor |  |  |  | Green | iSupplier Deployment | Completed | 100% | 2026-04-23 | 2026-05-06 |  |  |  |  | 9d |  | 111 | [11 empty] | 2026-04-23 | 2026-05-06 | 0
#UNPARSEABLE | #UNPARSEABLE | #UNPARSEABLE |  | #UNPARSEABLE | 3 | Rohan Kapoor |  |  |  | Green | Design & Development on STAGING Set UP | Completed | 100% | 2026-04-23 | 2026-05-06 |  |  |  |  | 9d |  | 111 | [11 empty] | 2026-04-23 | 2026-05-06 | 0
#UNPARSEABLE | #UNPARSEABLE | #UNPARSEABLE |  | #UNPARSEABLE | 4 | Rohan Kapoor |  |  |  | Green | Users,Roles,Workflow & View Definition Configuration | Completed | 100% | 2026-04-23 | 2026-04-28 |  |  |  |  | 4d |  | 106 | [11 empty] | 2026-04-23 | 2026-04-28 | 0
#UNPARSEABLE | #UNPARSEABLE | #UNPARSEABLE |  | #UNPARSEABLE | 5 | Rohan Kapoor |  |  |  | Green | Configure User Roles, View Definition and Workflow as per IAD | Completed | 100% | 2026-04-23 | 2026-04-27 |  |  |  |  | 3d | 42 | 0 | TRUE | [7 empty] | Zycus Product Specialist |  |  | 2026-04-23 | 2026-04-27 | 0
#UNPARSEABLE | #UNPARSEABLE | #UNPARSEABLE |  | #UNPARSEABLE | 5 | Rohan Kapoor |  |  |  | Green | Solvara to provide feedback | Completed | 100% | 2026-04-28 | 2026-04-28 |  |  |  |  | 1d | 82 | 0 | TRUE | [7 empty] | Solvara Core Project Team, Solvara Subject Matter Expert |  |  | 2026-04-28 | 2026-04-28 | 0
#UNPARSEABLE | #UNPARSEABLE | #UNPARSEABLE |  | #UNPARSEABLE | 4 | Rohan Kapoor |  |  |  | Green | Pre-UAT on STAGING Set UP | Completed | 100% | 2026-04-29 | 2026-05-06 |  |  |  |  | 5d |  | 4 | [11 empty] | 2026-04-29 | 2026-05-06 | 0
#UNPARSEABLE | #UNPARSEABLE | #UNPARSEABLE |  | #UNPARSEABLE | 5 | Rohan Kapoor |  |  |  | Green | Pre-UAT - Provide End to end walkthrough of configured iSupplier to Solvara | Completed | 100% | 2026-04-29 | 2026-04-30 |  |  |  |  | 2d | 81 | 0 | TRUE | [7 empty] | Zycus Consultant, Zycus Product Specialist |  |  | 2026-04-29 | 2026-04-30 | 0
#UNPARSEABLE | #UNPARSEABLE | #UNPARSEABLE |  | #UNPARSEABLE | 5 | Rohan Kapoor |  |  |  | Green | Provide feedback - if any for iSupplier configuration | Completed | 100% | 2026-05-04 | 2026-05-04 |  |  |  |  | 1d | 85 | 0 | TRUE | [7 empty] | Solvara Project Team |  |  | 2026-05-04 | 2026-05-04 | 0
#UNPARSEABLE | #UNPARSEABLE | #UNPARSEABLE |  | #UNPARSEABLE | 5 | Rohan Kapoor |  |  |  | Green | Zycus to incorporate feedback - as applicable and share final version of Implementation Approach Document [IAD] | Completed | 100% | 2026-05-05 | 2026-05-06 |  |  |  |  | 2d | 85, 86 | 109 | [8 empty] | Zycus Consultant |  |  | 2026-05-05 | 2026-05-06 | 0
#UNPARSEABLE | #UNPARSEABLE | #UNPARSEABLE |  | #UNPARSEABLE | 5 | Rohan Kapoor |  |  |  | Green | Sign off on Pre-UAT and final version of IAD | Completed | 100% | 2026-05-06 | 2026-05-06 |  |  |  |  | 0 | 87 | 109 | [8 empty] | Solvara Project Manager, Zycus Project Manager |  |  | 2026-05-06 | 2026-05-06 | 0
#UNPARSEABLE | #UNPARSEABLE | #UNPARSEABLE |  | #UNPARSEABLE | 2 | Rohan Kapoor |  |  |  | Green | iSupplier: Conclude Functional Configuration | Completed | 100% | 2026-05-06 | 2026-05-06 |  |  |  |  | 0 | 84 | 4 | [11 empty] | 2026-05-06 | 2026-05-06 | 0
#UNPARSEABLE | #UNPARSEABLE | #UNPARSEABLE |  | #UNPARSEABLE | 2 | Rohan Kapoor |  |  |  | Green | Value KPI Report creation on Staging | Completed | 100% | 2026-05-07 | 2026-05-08 |  |  |  |  | 2d | 94, 81, #REF | 105 | [8 empty] | Solvara Project Group, Zycus Product Specialist, Zycus Project Manager |  |  | 2026-05-12 | 2026-05-13 | 3d
#UNPARSEABLE | #UNPARSEABLE | #UNPARSEABLE |  | #UNPARSEABLE | 2 | Rohan Kapoor |  |  |  | Green | Value KPI Report demo on Staging | Completed | 100% | 2026-05-14 | 2026-05-15 |  |  |  |  | 2d | 90SS +5d | 102 | [8 empty] | Solvara Project Group, Zycus Product Specialist, Zycus Project Manager |  |  | 2026-05-19 | 2026-05-20 | 3d
#UNPARSEABLE | #UNPARSEABLE | #UNPARSEABLE |  | #UNPARSEABLE | 1 | Rohan Kapoor |  |  |  | Green | User Acceptance Testing (UAT) Phase I | Completed | 100% | 2026-05-04 | 2026-05-20 |  |  |  |  | 13d |  | 101 | [11 empty] | 2026-05-04 | 2026-06-16 | 18d
#UNPARSEABLE | #UNPARSEABLE | #UNPARSEABLE |  | #UNPARSEABLE | 2 | Rohan Kapoor |  |  |  | Green | Prepare for UAT | Completed | 100% | 2026-05-04 | 2026-05-13 |  |  |  |  | 8d |  | 4 | [11 empty] | 2026-05-04 | 2026-05-13 | 0
#UNPARSEABLE | #UNPARSEABLE | #UNPARSEABLE |  | #UNPARSEABLE | 3 | Rohan Kapoor |  |  |  | Green | Prepare the UAT Approach | Completed | 100% | 2026-05-04 | 2026-05-05 |  |  |  |  | 2d | 85 | 107 | [8 empty] | Zycus Product Specialist, Zycus Project Manager |  |  | 2026-05-04 | 2026-05-05 | 0
#UNPARSEABLE | #UNPARSEABLE | #UNPARSEABLE |  | #UNPARSEABLE | 3 | Rohan Kapoor |  |  |  | Green | Finalize and agree on UAT Approach | Completed | 100% | 2026-05-06 | 2026-05-06 |  |  |  |  | 1d | 94 | 107 | [8 empty] | Solvara Core Project Team, Solvara Project Manager |  |  | 2026-05-06 | 2026-05-06 | 0
#UNPARSEABLE | #UNPARSEABLE | #UNPARSEABLE |  | #UNPARSEABLE | 3 | Rohan Kapoor |  |  |  | Green | Provide users & roles on STAGING required for UAT | Completed | 100% | 2026-05-05 | 2026-05-08 |  |  |  |  | 4d | 86 | 0 | TRUE | [7 empty] | Solvara Project Manager, Solvara Project Team, Solvara SME |  |  | 2026-05-05 | 2026-05-08 | 0
#UNPARSEABLE | #UNPARSEABLE | #UNPARSEABLE |  | #UNPARSEABLE | 3 | Rohan Kapoor |  |  |  | Green | Create users on STAGING set for UAT group | Completed | 100% | 2026-05-11 | 2026-05-13 |  |  |  |  | 3d | 96 | 0 | TRUE | [7 empty] | Zycus Product Specialist |  |  | 2026-05-11 | 2026-05-13 | 0
#UNPARSEABLE | #UNPARSEABLE | #UNPARSEABLE |  | #UNPARSEABLE | 3 | Rohan Kapoor |  |  |  | Green | Provide Standard Test Cases | Completed | 100% | 2026-05-07 | 2026-05-08 |  |  |  |  | 2d | 95 | 107 | [8 empty] | Zycus Consultant, Zycus Product Specialist |  |  | 2026-05-07 | 2026-05-08 | 0
#UNPARSEABLE | #UNPARSEABLE | #UNPARSEABLE |  | #UNPARSEABLE | 3 | Rohan Kapoor |  |  |  | Green | Finalize Test Cases | Completed | 100% | 2026-05-11 | 2026-05-12 |  |  |  |  | 2d | 98 | 107 | [8 empty] | Solvara Core Project Team |  |  | 2026-05-11 | 2026-05-12 | 0
#UNPARSEABLE | #UNPARSEABLE | #UNPARSEABLE |  | #UNPARSEABLE | 3 | Rohan Kapoor |  |  |  | Green | Quality Reviews | Completed | 100% | 2026-05-07 | 2026-05-08 |  |  |  |  | 2d |  | 109 | [11 empty] | 2026-05-12 | 2026-05-13 | 3d
#UNPARSEABLE | #UNPARSEABLE | #UNPARSEABLE |  | #UNPARSEABLE | 4 | Rohan Kapoor |  |  |  | Green | Schedule for quality check | Completed | 100% | 2026-05-07 | 2026-05-07 |  |  |  |  | 1d | 88, 75 | 109 | [8 empty] | Zycus Product Specialist |  |  | 2026-05-12 | 2026-05-12 | 3d
#UNPARSEABLE | #UNPARSEABLE | #UNPARSEABLE |  | #UNPARSEABLE | 4 | Rohan Kapoor |  |  |  | Green | Perform quality checks, PSRs as per quality checklist and submit to QC team | Completed | 100% | 2026-05-08 | 2026-05-08 |  |  |  |  | 1d | 101 | 109 | [8 empty] | Zycus Product Specialist |  |  | 2026-05-13 | 2026-05-13 | 3d
#UNPARSEABLE | #UNPARSEABLE | #UNPARSEABLE |  | #UNPARSEABLE | 4 | Rohan Kapoor |  |  |  | Green | Quality Check by Zycus QC team | Completed | 100% | 2026-05-08 | 2026-05-08 |  |  |  |  | 0 | 102 | 109 | [8 empty] | Zycus Quality Team |  |  | 2026-05-13 | 2026-05-13 | 3d
#UNPARSEABLE | #UNPARSEABLE | #UNPARSEABLE |  | #UNPARSEABLE | 2 | Rohan Kapoor |  |  |  | Green | End-to-End UAT | Completed | 100% | 2026-05-14 | 2026-05-20 |  |  |  |  | 5d |  | 101 | [11 empty] | 2026-05-14 | 2026-06-16 | 18d
#UNPARSEABLE | #UNPARSEABLE | #UNPARSEABLE |  | #UNPARSEABLE | 3 | Rohan Kapoor |  |  |  | Green | UAT for iContract and iSupplier | Completed | 100% | 2026-05-14 | 2026-05-18 |  |  |  |  | 3d | 93, 89, 75 | 0 | TRUE | [7 empty] | Solvara Core Project Team |  |  | 2026-05-14 | 2026-05-18 | 0
#UNPARSEABLE | #UNPARSEABLE | #UNPARSEABLE |  | #UNPARSEABLE | 3 | Rohan Kapoor |  |  |  | Green | Defect Analysis & UAT Feedback incorporation and share Test Closure Memo | Completed | 100% | 2026-05-14 | 2026-05-19 |  |  |  |  | 4d | 105SS | 0 | TRUE | [7 empty] | Zycus Project Team |  |  | 2026-05-14 | 2026-05-19 | 0
#UNPARSEABLE | #UNPARSEABLE | #UNPARSEABLE |  | #UNPARSEABLE | 3 | Rohan Kapoor |  |  |  | Green | Solvara to provide sign off on Test Closure Memo | Completed | 100% | 2026-05-20 | 2026-05-20 |  |  |  |  | 1d | 106 | 0 | TRUE | [7 empty] | Solvara Core Project Team, Solvara Project Manager |  |  | 2026-05-20 | 2026-05-20 | 0
#UNPARSEABLE | #UNPARSEABLE | #UNPARSEABLE |  | #UNPARSEABLE | 1 | Rohan Kapoor |  |  |  | Green | UAT Completion I | Completed | 100% | 2026-05-20 | 2026-05-20 |  |  |  |  | 0 | 107 | 69 | [11 empty] | 2026-05-20 | 2026-05-20 | 0
#UNPARSEABLE | #UNPARSEABLE | #UNPARSEABLE |  | #UNPARSEABLE | 1 | Rohan Kapoor |  |  |  | Green | Value KPI Sign-off | Completed | 100% | 2026-05-18 | 2026-05-18 |  |  |  |  | 0 | 91, 105 | 101 | [8 empty] | Solvara Project Group, Zycus Product Specialist, Zycus Project Manager |  |  | 2026-05-20 | 2026-05-20 | 2d
#UNPARSEABLE | #UNPARSEABLE | #UNPARSEABLE |  | #UNPARSEABLE | 1 | Rohan Kapoor |  |  |  | Red | Training Phase I | In Progress | 77% | 2026-05-19 | 2026-05-28 |  |  |  |  | 7d |  | 96 | [11 empty] | 2026-05-19 | 2026-06-22 | 17d
#UNPARSEABLE | #UNPARSEABLE | #UNPARSEABLE |  | #UNPARSEABLE | 2 | Rohan Kapoor |  |  |  | Green | Training Preparation | Completed | 100% | 2026-05-19 | 2026-05-21 |  |  |  |  | 3d |  | 100 | [11 empty] | 2026-05-19 | 2026-05-21 | 0
#UNPARSEABLE | #UNPARSEABLE | #UNPARSEABLE |  | #UNPARSEABLE | 3 | Rohan Kapoor |  |  |  | Green | Training Approach and Schedule finalization | Completed | 100% | 2026-05-19 | 2026-05-20 |  |  |  |  | 2d | 105 | 96 | [8 empty] | Solvara Project Manager, Zycus Project Manager, Zycus University |  |  | 2026-05-19 | 2026-05-20 | 0
#UNPARSEABLE | #UNPARSEABLE | #UNPARSEABLE |  | #UNPARSEABLE | 3 | Rohan Kapoor |  |  |  | Green | Training Agenda Finalization | Completed | 100% | 2026-05-21 | 2026-05-21 |  |  |  |  | 1d | 112 | 96 | [8 empty] | Solvara Project Manager, Zycus University Trainer |  |  | 2026-05-21 | 2026-05-21 | 0
#UNPARSEABLE | #UNPARSEABLE | #UNPARSEABLE |  | #UNPARSEABLE | 2 | Rohan Kapoor |  |  |  | Red | Train The Trainer | In Progress | 60% | 2026-05-22 | 2026-05-28 |  |  |  |  | 4d |  | 96 | [11 empty] | 2026-05-22 | 2026-06-22 | 17d
#UNPARSEABLE | #UNPARSEABLE | #UNPARSEABLE |  | #UNPARSEABLE | 3 | Rohan Kapoor |  |  |  | Green | iContract + Merlin for Contract Training | Completed | 100% | 2026-05-22 | 2026-05-25 |  |  |  |  | 2d | 107, 113 | 96 | [8 empty] | Solvara Project Team, Zycus University Trainer |  |  | 2026-05-22 | 2026-05-25 | 0
#UNPARSEABLE | #UNPARSEABLE | #UNPARSEABLE |  | #UNPARSEABLE | 3 | Rohan Kapoor |  |  |  | Green | iSupplier Training | Completed | 100% | 2026-05-26 | 2026-05-26 |  |  |  |  | 1d | 115 | 97 | [8 empty] | Solvara Project Team, Zycus University Trainer |  |  | 2026-05-26 | 2026-05-26 | 0
#UNPARSEABLE | #UNPARSEABLE | #UNPARSEABLE |  | #UNPARSEABLE | 3 | Rohan Kapoor |  |  |  | Red | Admin Training | Not Started | 0% | 2026-05-26 | 2026-05-28 |  |  |  |  | 2d | 115 | 96 | [8 empty] | Solvara Project Team, Zycus University Trainer |  |  | 2026-06-19 | 2026-06-22 | 17d
#UNPARSEABLE | #UNPARSEABLE | #UNPARSEABLE |  | #UNPARSEABLE | 1 | Rohan Kapoor |  |  |  | Green | Training Completion | Completed | 100% | 2026-05-28 | 2026-05-28 |  |  |  |  | 0 | 117 | 96 | [11 empty] | 2026-06-22 | 2026-06-22 | 17d
#UNPARSEABLE | #UNPARSEABLE | #UNPARSEABLE |  | #UNPARSEABLE | 1 | Rohan Kapoor |  |  |  | Green | Production Migration Phase I | Completed | 100% | 2026-05-19 | 2026-06-03 |  |  |  |  | 11d |  | 92 | [11 empty] | 2026-05-19 | 2026-06-23 | 14d
#UNPARSEABLE | #UNPARSEABLE | #UNPARSEABLE |  | #UNPARSEABLE | 2 | Rohan Kapoor |  |  |  | Green | Migration of Solution from STAGING Environment to PRODUCTION | Completed | 100% | 2026-05-19 | 2026-06-03 |  |  |  |  | 11d |  | 92 | [11 empty] | 2026-05-19 | 2026-06-23 | 14d
#UNPARSEABLE | #UNPARSEABLE | #UNPARSEABLE |  | #UNPARSEABLE | 3 | Rohan Kapoor |  |  |  | Green | Log ticket for PRODUCTION tenant creation | Completed | 100% | 2026-05-19 | 2026-05-19 |  |  |  |  | 1d | 105 | 91 | [8 empty] | Zycus Product Specialist |  |  | 2026-05-19 | 2026-05-19 | 0
#UNPARSEABLE | #UNPARSEABLE | #UNPARSEABLE |  | #UNPARSEABLE | 3 | Rohan Kapoor |  |  |  | Green | Configuration migration to PRODUCTION for iContract & iSupplier | Completed | 100% | 2026-05-21 | 2026-05-28 |  |  |  |  | 5d | 121, 107 | 91 | [8 empty] | Zycus Product Specialist |  |  | 2026-05-21 | 2026-05-28 | 0
#UNPARSEABLE | #UNPARSEABLE | #UNPARSEABLE |  | #UNPARSEABLE | 3 | Rohan Kapoor |  |  |  | Green | Provide the final list of users to be created on PRODUCTION | Completed | 100% | 2026-05-21 | 2026-05-25 |  |  |  |  | 3d | 108 | 69 | [8 empty] | Solvara Holdings SME, Solvara Project Manager, TKC Holdings Project Team |  |  | 2026-05-21 | 2026-05-25 | 0
#UNPARSEABLE | #UNPARSEABLE | #UNPARSEABLE |  | #UNPARSEABLE | 3 | Rohan Kapoor |  |  |  | Green | Creation of Specified Users as per roles | Completed | 100% | 2026-05-26 | 2026-06-01 |  |  |  |  | 4d | 123 | 69 | [8 empty] | Zycus Product Specialist |  |  | 2026-05-26 | 2026-06-01 | 0
#UNPARSEABLE | #UNPARSEABLE | #UNPARSEABLE |  | #UNPARSEABLE | 3 | Rohan Kapoor |  |  |  | Green | WordConnect Installation at Solvara's end | Completed | 100% | 2026-05-29 | 2026-06-01 |  |  |  |  | 2d | 122 | 94 | [8 empty] | Solvara IT Team, Solvara Project Manager |  |  | 2026-05-29 | 2026-06-01 | 0
#UNPARSEABLE | #UNPARSEABLE | #UNPARSEABLE |  | #UNPARSEABLE | 3 | Rohan Kapoor |  |  |  | Green | Migration of SSO | Completed | 100% | 2026-05-25 | 2026-06-03 |  |  |  |  | 7d |  | 92 | [11 empty] | 2026-05-25 | 2026-06-03 | 0
#UNPARSEABLE | #UNPARSEABLE | #UNPARSEABLE |  | #UNPARSEABLE | 4 | Rohan Kapoor |  |  |  | Green | PRODUCTION setup with standard configuration | Completed | 100% | 2026-05-25 | 2026-05-26 |  |  |  |  | 2d | 122SS +2d | 91 | [8 empty] | Zycus SSO Team |  |  | 2026-05-25 | 2026-05-26 | 0
#UNPARSEABLE | #UNPARSEABLE | #UNPARSEABLE |  | #UNPARSEABLE | 4 | Rohan Kapoor |  |  |  | Green | Exchange of certificates to be used | Completed | 100% | 2026-05-28 | 2026-05-28 |  |  |  |  | 1d | 127 | 95 | [8 empty] | Solvara IT Team, Zycus SSO Team |  |  | 2026-05-28 | 2026-05-28 | 0
#UNPARSEABLE | #UNPARSEABLE | #UNPARSEABLE |  | #UNPARSEABLE | 4 | Rohan Kapoor |  |  |  | Green | Registration of Service Provider URL for client | Completed | 100% | 2026-05-29 | 2026-05-29 |  |  |  |  | 1d | 128 | 95 | [8 empty] | Zycus SSO Team |  |  | 2026-05-29 | 2026-05-29 | 0
#UNPARSEABLE | #UNPARSEABLE | #UNPARSEABLE |  | #UNPARSEABLE | 4 | Rohan Kapoor |  |  |  | Green | Registration TMS URL specific to client | Completed | 100% | 2026-05-28 | 2026-05-28 |  |  |  |  | 1d | 127 | 95 | [8 empty] | Zycus SSO Team |  |  | 2026-05-28 | 2026-05-28 | 0
#UNPARSEABLE | #UNPARSEABLE | #UNPARSEABLE |  | #UNPARSEABLE | 4 | Rohan Kapoor |  |  |  | Green | Configuration of Web Server for service Provider application | Completed | 100% | 2026-05-29 | 2026-05-29 |  |  |  |  | 1d | 130 | 95 | [8 empty] | Zycus SSO Team |  |  | 2026-05-29 | 2026-05-29 | 0
#UNPARSEABLE | #UNPARSEABLE | #UNPARSEABLE |  | #UNPARSEABLE | 4 | Rohan Kapoor |  |  |  | Green | Service Provider application deployment for client and sanity of the deployed setup | Completed | 100% | 2026-05-29 | 2026-05-29 |  |  |  |  | 1d | 130 | 95 | [8 empty] | Zycus SSO Team |  |  | 2026-05-29 | 2026-05-29 | 0
#UNPARSEABLE | #UNPARSEABLE | #UNPARSEABLE |  | #UNPARSEABLE | 4 | Rohan Kapoor |  |  |  | Green | Raise internal ticket for configuration of service provider set up & PRODUCTION URL Change | Completed | 100% | 2026-05-26 | 2026-05-26 |  |  |  |  | 1d | 127FS -1d | 92 | [8 empty] | Zycus SSO Team |  |  | 2026-05-26 | 2026-05-26 | 0
#UNPARSEABLE | #UNPARSEABLE | #UNPARSEABLE |  | #UNPARSEABLE | 4 | Rohan Kapoor |  |  |  | Green | Configuration of Service Provider setup | Completed | 100% | 2026-05-28 | 2026-05-29 |  |  |  |  | 2d | 133 | 92 | [8 empty] | Zycus SSO Team |  |  | 2026-05-28 | 2026-05-29 | 0
#UNPARSEABLE | #UNPARSEABLE | #UNPARSEABLE |  | #UNPARSEABLE | 4 | Rohan Kapoor |  |  |  | Green | PRODUCTION URL change | Completed | 100% | 2026-06-01 | 2026-06-02 |  |  |  |  | 2d |  | 93 | [11 empty] | 2026-06-01 | 2026-06-02 | 0
#UNPARSEABLE | #UNPARSEABLE | #UNPARSEABLE |  | #UNPARSEABLE | 5 | Rohan Kapoor |  |  |  | Green | Configuring DSSO URL for all the respective product | Completed | 100% | 2026-06-01 | 2026-06-01 |  |  |  |  | 1d | 134 | 92 | [8 empty] | Zycus SSO Team |  |  | 2026-06-01 | 2026-06-01 | 0
#UNPARSEABLE | #UNPARSEABLE | #UNPARSEABLE |  | #UNPARSEABLE | 5 | Rohan Kapoor |  |  |  | Green | Testing of SSO login on PRODUCTION set up | Completed | 100% | 2026-06-02 | 2026-06-02 |  |  |  |  | 1d | 136 | 92 | [8 empty] | Solvara IT Team, TKC Holdings Project Team |  |  | 2026-06-02 | 2026-06-02 | 0
#UNPARSEABLE | #UNPARSEABLE | #UNPARSEABLE |  | #UNPARSEABLE | 4 | Rohan Kapoor |  |  |  | Green | Sign off on SSO Implementation | Completed | 100% | 2026-06-03 | 2026-06-03 |  |  |  |  | 1d | 137 | 92 | [8 empty] | Solvara Project Manager |  |  | 2026-06-03 | 2026-06-03 | 0
#UNPARSEABLE | #UNPARSEABLE | #UNPARSEABLE |  | #UNPARSEABLE | 3 | Rohan Kapoor |  |  |  | Green | Quality Reviews | Completed | 100% | 2026-06-02 | 2026-06-03 |  |  |  |  | 2d |  | 92 | [11 empty] | 2026-06-02 | 2026-06-03 | 0
#UNPARSEABLE | #UNPARSEABLE | #UNPARSEABLE |  | #UNPARSEABLE | 4 | Rohan Kapoor |  |  |  | Green | Schedule for quality check | Completed | 100% | 2026-06-02 | 2026-06-02 |  |  |  |  | 1d | 124 | 69 | [8 empty] | Zycus Product Specialist |  |  | 2026-06-02 | 2026-06-02 | 0
#UNPARSEABLE | #UNPARSEABLE | #UNPARSEABLE |  | #UNPARSEABLE | 4 | Rohan Kapoor |  |  |  | Green | Perform quality checks, PSRs as per quality checklist and submit to QC team | Completed | 100% | 2026-06-03 | 2026-06-03 |  |  |  |  | 1d | 140 | 69 | [8 empty] | Zycus Product Specialist |  |  | 2026-06-03 | 2026-06-03 | 0
#UNPARSEABLE | #UNPARSEABLE | #UNPARSEABLE |  | #UNPARSEABLE | 4 | Rohan Kapoor |  |  |  | Green | Quality Check by Zycus QC team | Completed | 100% | 2026-06-03 | 2026-06-03 |  |  |  |  | 0 | 141 | 69 | [8 empty] | Zycus Quality Team |  |  | 2026-06-03 | 2026-06-03 | 0
#UNPARSEABLE | #UNPARSEABLE | #UNPARSEABLE |  | #UNPARSEABLE | 1 | Rohan Kapoor |  |  |  | Green | KPI Reports to be migrated on PROD | Completed | 100% | 2026-05-29 | 2026-06-01 |  |  |  |  | 2d | 109, 122 | 94 | [8 empty] | Solvara Project Group, Zycus Product Specialist, Zycus Project Manager |  |  | 2026-05-29 | 2026-06-01 | 0
#UNPARSEABLE | #UNPARSEABLE | #UNPARSEABLE |  | #UNPARSEABLE | 1 | Rohan Kapoor |  |  |  | Green | Sanity on Production for iContract and iSupplier | Completed | 100% | 2026-06-04 | 2026-06-05 |  |  |  |  | 2d | 142 | 69 | [8 empty] | Solvara IT Team, Solvara Integration Team, Solvara Project Manager, Solvara SME, Solvara Subject Matter Expert |  |  | 2026-06-04 | 2026-06-05 | 0
#UNPARSEABLE | #UNPARSEABLE | #UNPARSEABLE |  | #UNPARSEABLE | 1 | Rohan Kapoor |  |  |  | Green | Go /No-go Check Point ( Meeting with Solvara) for iContract & iSupplier | Completed | 100% | 2026-06-08 | 2026-06-08 |  |  |  |  | 1d | 144 | 69 | [8 empty] | Solvara Project Manager |  |  | 2026-06-08 | 2026-06-08 | 0
#UNPARSEABLE | #UNPARSEABLE | #UNPARSEABLE |  | #UNPARSEABLE | 1 | Rohan Kapoor |  |  |  | Green | Release Zycus system to all users for iContract and iSupplier | Completed | 100% | 2026-06-08 | 2026-06-08 |  |  |  |  | 0 | 145 | 69 | [8 empty] | Zycus Product Specialist |  |  | 2026-06-08 | 2026-06-08 | 0
#UNPARSEABLE | #UNPARSEABLE | #UNPARSEABLE |  | #UNPARSEABLE | 1 | Rohan Kapoor |  |  |  | Green | Production Go-Live Phase I | Completed | 100% | 2026-06-08 | 2026-06-08 |  |  |  |  | 0 | 146 | 69 | [11 empty] | 2026-06-24 | 2026-06-24 | 12d
#UNPARSEABLE | #UNPARSEABLE | #UNPARSEABLE |  | #UNPARSEABLE | 1 | Rohan Kapoor |  |  |  | Red | Hypercare Phase I | In Progress | 25% | 2026-06-09 | 2026-07-06 |  |  |  |  | 20d | 147 | 69 | [8 empty] | Solvara IT Team, Solvara Integration Team, Solvara Project Group, Zycus Consultant, Zycus Integration Team, Zycus Product Specialist, Zycus Project Manager |  |  | 2026-06-25 | 2026-07-23 | 13d
#UNPARSEABLE | #UNPARSEABLE | #UNPARSEABLE |  | #UNPARSEABLE | 1 | Rohan Kapoor |  |  |  | Red | Configuration Validation & Documentation | In Progress | 26% | 2026-06-19 | 2026-07-22 |  |  |  |  | 24d |  | 57
#UNPARSEABLE | #UNPARSEABLE | #UNPARSEABLE |  | #UNPARSEABLE | 2 | Rohan Kapoor |  |  |  | Yellow | Requirement Workshop | In Progress | 51% | 2026-06-19 | 2026-07-15 |  |  |  |  | 19d |  | 62
#UNPARSEABLE | #UNPARSEABLE | #UNPARSEABLE |  | #UNPARSEABLE | 3 | Rohan Kapoor |  |  |  | Red | iSource Configuration Documentation Workshop | In Progress | 80% | 2026-06-29 | 2026-07-02 |  |  |  |  | 4d | 152 | 0 | TRUE | [7 empty] | Solvara Project Team, Solvara SME, Zycus Project Team
#UNPARSEABLE | #UNPARSEABLE | #UNPARSEABLE |  | #UNPARSEABLE | 3 | Rohan Kapoor |  |  |  | Red | eProc, eInvoice and Merlin APSD Configuration Documentation Workshop | In Progress | 50% | 2026-06-19 | 2026-06-26 |  |  |  |  | 6d | 107FS +20d | 0 | TRUE | [7 empty] | Solvara Project Team, Solvara SME, Zycus Project Team
#UNPARSEABLE | #UNPARSEABLE | #UNPARSEABLE |  | #UNPARSEABLE | 3 | Rohan Kapoor |  |  |  | Green | CLM Additional Approval Workflow Documentation Workshop | Not Started | 0% | 2026-07-03 | 2026-07-08 |  |  |  |  | 4d | 151 | 0 | TRUE | [7 empty] | Solvara Project Team, Solvara SME, Zycus Project Team
#UNPARSEABLE | #UNPARSEABLE | #UNPARSEABLE |  | #UNPARSEABLE | 3 | Rohan Kapoor |  |  |  | Green | Merlin Intake Configuration Documentation Workshop | In Progress | 80% | 2026-07-09 | 2026-07-15 |  |  |  |  | 5d | 153 | 0 | TRUE | [7 empty] | Solvara Project Team, Solvara SME, Zycus Project Team
#UNPARSEABLE | #UNPARSEABLE | #UNPARSEABLE |  | #UNPARSEABLE | 3 | Rohan Kapoor |  |  |  | Green | Integration Configuration Documentation Workshop ( eInovoice, iContract) | Not Started | 0% | 2026-07-03 | 2026-07-03 |  |  |  |  | 1d | 151, 152 | 70 | [8 empty] | Solvara Project Team, Solvara SME, Zycus Project Team
#UNPARSEABLE | #UNPARSEABLE | #UNPARSEABLE |  | #UNPARSEABLE | 2 | Rohan Kapoor |  |  |  | Red | Configuration Documentation | Not Started | 0% | 2026-06-29 | 2026-07-22 |  |  |  |  | 18d |  | 57
#UNPARSEABLE | #UNPARSEABLE | #UNPARSEABLE |  | #UNPARSEABLE | 3 | Rohan Kapoor |  |  |  | Green | iSource Configuration Documentation | Not Started | 0% | 2026-07-03 | 2026-07-03 |  |  |  |  | 1d | 151 | 70 | [8 empty] | Solvara Core Project Team, Solvara Project Manager, Zycus Merlin Product Team, Zycus Project Manager, Zycus Project Team
#UNPARSEABLE | #UNPARSEABLE | #UNPARSEABLE |  | #UNPARSEABLE | 3 | Rohan Kapoor |  |  |  | Red | eProc, eInvoice and Merlin APSD Configuration Documentation | Not Started | 0% | 2026-06-29 | 2026-06-29 |  |  |  |  | 1d | 152 | 23 | [8 empty] | Solvara Core Project Team, Solvara Project Manager, Zycus Merlin Product Team, Zycus Project Manager, Zycus Project Team
#UNPARSEABLE | #UNPARSEABLE | #UNPARSEABLE |  | #UNPARSEABLE | 3 | Rohan Kapoor |  |  |  | Green | CLM Configuration Documentation | Not Started | 0% | 2026-07-09 | 2026-07-09 |  |  |  |  | 1d | 153 | 66 | [8 empty] | Solvara Core Project Team, Solvara Project Manager, Zycus Merlin Product Team, Zycus Project Manager, Zycus Project Team
#UNPARSEABLE | #UNPARSEABLE | #UNPARSEABLE |  | #UNPARSEABLE | 3 | Rohan Kapoor |  |  |  | Green | iSupplier Configuration Documentation | Not Started | 0% | 2026-07-09 | 2026-07-09 |  |  |  |  | 0 | 159 | 66 | [8 empty] | Solvara Core Project Team, Solvara Project Manager, Zycus Merlin Product Team, Zycus Project Manager, Zycus Project Team
#UNPARSEABLE | #UNPARSEABLE | #UNPARSEABLE |  | #UNPARSEABLE | 3 | Rohan Kapoor |  |  |  | Green | Merlin Intake Configuration Documentation | Not Started | 0% | 2026-07-16 | 2026-07-16 |  |  |  |  | 1d | 154 | 0 | TRUE | [7 empty] | Solvara Core Project Team, Solvara Project Manager, Zycus Merlin Product Team, Zycus Project Manager, Zycus Project Team
#UNPARSEABLE | #UNPARSEABLE | #UNPARSEABLE |  | #UNPARSEABLE | 3 | Rohan Kapoor |  |  |  | Green | IAD Review for all modules | Not Started | 0% | 2026-07-17 | 2026-07-20 |  |  |  |  | 2d | 161 | 0 | TRUE | [7 empty] | Solvara Project Manager
#UNPARSEABLE | #UNPARSEABLE | #UNPARSEABLE |  | #UNPARSEABLE | 3 | Rohan Kapoor |  |  |  | Green | Solvara to review and Sign-off IAD Draft | Not Started | 0% | 2026-07-21 | 2026-07-21 |  |  |  |  | 1d | 162 | 0 | TRUE | [7 empty] | Solvara Project Manager
#UNPARSEABLE | #UNPARSEABLE | #UNPARSEABLE |  | #UNPARSEABLE | 3 | Rohan Kapoor |  |  |  | Green | Value Realization Target Discussion | Not Started | 0% | 2026-07-22 | 2026-07-22 |  |  |  |  | 1d | 163 | 57 | [8 empty] | Solvara Project Group, Zycus Product Specialist, Zycus Project Manager
#UNPARSEABLE | #UNPARSEABLE | #UNPARSEABLE |  | #UNPARSEABLE | 2 | Rohan Kapoor |  |  |  | Green | Configuration Documentation concluded | Not Started | 0% | 2026-07-22 | 2026-07-22 |  |  |  |  | 0 | 156 | 57
#UNPARSEABLE | #UNPARSEABLE | #UNPARSEABLE |  | #UNPARSEABLE | 2 | Rohan Kapoor |  |  |  | Green | First draft IAD Sign-off | Not Started | 0% | 2026-07-21 | 2026-07-21 |  |  |  |  | 0 | 163 | 58
#UNPARSEABLE | #UNPARSEABLE | #UNPARSEABLE |  | #UNPARSEABLE | 1 | Rohan Kapoor |  |  |  | Yellow | eProc and eInvoice and Merlin APSD | In Progress | 21% | 2026-06-19 | 2026-08-04 |  |  |  |  | 33d |  | 48
#UNPARSEABLE | #UNPARSEABLE | #UNPARSEABLE |  | #UNPARSEABLE | 2 | Rohan Kapoor |  |  |  | Green | eProc-einvoice Deployment | In Progress | 8% | 2026-07-02 | 2026-07-20 |  |  |  |  | 13d |  | 59
#UNPARSEABLE | #UNPARSEABLE | #UNPARSEABLE |  | #UNPARSEABLE | 3 | Rohan Kapoor |  |  |  | Green | Functional Configuration Finalization on STAGING set Up | In Progress | 8% | 2026-07-02 | 2026-07-20 |  |  |  |  | 13d |  | 59
#UNPARSEABLE | #UNPARSEABLE | #UNPARSEABLE |  | #UNPARSEABLE | 4 | Rohan Kapoor |  |  |  | Green | User Roles configuration | In Progress | 50% | 2026-07-02 | 2026-07-03 |  |  |  |  | 2d | 158FS +2d | 23 | [8 empty] | Zycus Product Specialist
#UNPARSEABLE | #UNPARSEABLE | #UNPARSEABLE |  | #UNPARSEABLE | 4 | Rohan Kapoor |  |  |  | Green | Admin settings configuration | Not Started | 0% | 2026-07-06 | 2026-07-07 |  |  |  |  | 2d | 170 | 23 | [8 empty] | Zycus Product Specialist
#UNPARSEABLE | #UNPARSEABLE | #UNPARSEABLE |  | #UNPARSEABLE | 4 | Rohan Kapoor |  |  |  | Green | Readiness for Pre-UAT | Not Started | 0% | 2026-07-08 | 2026-07-08 |  |  |  |  | 1d | 171 | 23 | [8 empty] | Zycus Product Specialist
#UNPARSEABLE | #UNPARSEABLE | #UNPARSEABLE |  | #UNPARSEABLE | 4 | Rohan Kapoor |  |  |  | Green | Pre-UAT on STAGING | Not Started | 0% | 2026-07-09 | 2026-07-20 |  |  |  |  | 8d |  | 59
#UNPARSEABLE | #UNPARSEABLE | #UNPARSEABLE |  | #UNPARSEABLE | 5 | Rohan Kapoor |  |  |  | Green | Pre-UAT - Provide End to end walkthrough of configured eProc and eInvoice to the Customer | Not Started | 0% | 2026-07-09 | 2026-07-10 |  |  |  |  | 2d | 172 | 23 | [8 empty] | Zycus Consultant, Zycus Product Specialist
#UNPARSEABLE | #UNPARSEABLE | #UNPARSEABLE |  | #UNPARSEABLE | 5 | Rohan Kapoor |  |  |  | Green | Provide feedback - if any for eProc configuration | Not Started | 0% | 2026-07-13 | 2026-07-15 |  |  |  |  | 3d | 174 | 23 | [8 empty] | Solvara Project Manager
#UNPARSEABLE | #UNPARSEABLE | #UNPARSEABLE |  | #UNPARSEABLE | 5 | Rohan Kapoor |  |  |  | Green | Zycus to incorporate feedback - as applicable and share final version of Implementation Approach Document [IAD] | Not Started | 0% | 2026-07-16 | 2026-07-20 |  |  |  |  | 3d | 174, 175 | 23 | [8 empty] | Zycus Consultant, Zycus Product Specialist
#UNPARSEABLE | #UNPARSEABLE | #UNPARSEABLE |  | #UNPARSEABLE | 5 | Rohan Kapoor |  |  |  | Green | Sign off on Pre-UAT and final version of IAD | Not Started | 0% | 2026-07-20 | 2026-07-20 |  |  |  |  | 0 | 176 | 21 | [8 empty] | Solvara Project Manager
#UNPARSEABLE | #UNPARSEABLE | #UNPARSEABLE |  | #UNPARSEABLE | 2 | Rohan Kapoor |  |  |  | Green | eProc : Conclude Functional Configuration | Not Started | 0% | 2026-07-20 | 2026-07-20 |  |  |  |  | 0 | 177 | 23
#UNPARSEABLE | #UNPARSEABLE | #UNPARSEABLE |  | #UNPARSEABLE | 2 | Rohan Kapoor |  |  |  | Red | Integrations eproc | In Progress | 47% | 2026-06-19 | 2026-07-09 |  |  |  |  | 15d |  | 66
#UNPARSEABLE | #UNPARSEABLE | #UNPARSEABLE |  | #UNPARSEABLE | 3 | Rohan Kapoor |  |  |  | Red | eProc Integration with SAP for Purchase order | In Progress | 47% | 2026-06-19 | 2026-07-09 |  |  |  |  | 15d |  | 66
#UNPARSEABLE | #UNPARSEABLE | #UNPARSEABLE |  | #UNPARSEABLE | 4 | Rohan Kapoor |  |  |  | Red | Integration Design | In Progress | 88% | 2026-06-19 | 2026-06-24 |  |  |  |  | 4d |  | 77
#UNPARSEABLE | #UNPARSEABLE | #UNPARSEABLE |  | #UNPARSEABLE | 5 | Rohan Kapoor |  |  |  | Green | Mapping activity for Integration | Completed | 100% | 2026-06-19 | 2026-06-22 |  |  |  |  | 2d | 152FS -6d | 24 | [8 empty] | Solvara Integration Team, Zycus Integration Specialist
#UNPARSEABLE | #UNPARSEABLE | #UNPARSEABLE |  | #UNPARSEABLE | 5 | Rohan Kapoor |  |  |  | Green | Share TDD for interface | Completed | 100% | 2026-06-23 | 2026-06-23 |  |  |  |  | 1d | 182 | 61 | [8 empty] | Zycus Integration Lead
#UNPARSEABLE | #UNPARSEABLE | #UNPARSEABLE |  | #UNPARSEABLE | 5 | Rohan Kapoor |  |  |  | Red | Review of TDD and share feedback with Zycus | In Progress | 50% | 2026-06-24 | 2026-06-24 |  |  |  |  | 1d | 183 | 61 | [8 empty] | Solvara Integration Team
#UNPARSEABLE | #UNPARSEABLE | #UNPARSEABLE |  | #UNPARSEABLE | 5 | Rohan Kapoor |  |  |  | Red | Sign off on TDD | Not Started | 0% | 2026-06-24 | 2026-06-24 |  |  |  |  | 0 | 184 | 61 | [8 empty] | Solvara Integration Team
#UNPARSEABLE | #UNPARSEABLE | #UNPARSEABLE |  | #UNPARSEABLE | 4 | Rohan Kapoor |  |  |  | Red | Development and Testing on STAGING Set Up | In Progress | 32% | 2026-06-25 | 2026-07-09 |  |  |  |  | 11d |  | 66
#UNPARSEABLE | #UNPARSEABLE | #UNPARSEABLE |  | #UNPARSEABLE | 5 | Rohan Kapoor |  |  |  | Green | Integration set up and development at Zycus | In Progress | 90% | 2026-06-29 | 2026-07-03 |  |  |  |  | 5d | 185FS +2d | 61 | [8 empty] | Zycus Integration Specialist
#UNPARSEABLE | #UNPARSEABLE | #UNPARSEABLE |  | #UNPARSEABLE | 5 | Rohan Kapoor |  |  |  | Red | Integration development at Solvara - as applicable | Not Started | 0% | 2026-06-25 | 2026-07-01 |  |  |  |  | 5d | 185 | 61 | [8 empty] | Solvara Integration Team
#UNPARSEABLE | #UNPARSEABLE | #UNPARSEABLE |  | #UNPARSEABLE | 5 | Rohan Kapoor |  |  |  | Green | Integration Unit Testing and Feedback Incorporation | Not Started | 0% | 2026-07-06 | 2026-07-06 |  |  |  |  | 1d | 187, 188 | 61 | [8 empty] | Zycus Integration Team
#UNPARSEABLE | #UNPARSEABLE | #UNPARSEABLE |  | #UNPARSEABLE | 5 | Rohan Kapoor |  |  |  | Green | Systems Integration Testing | Not Started | 0% | 2026-07-07 | 2026-07-09 |  |  |  |  | 3d |  | 66
#UNPARSEABLE | #UNPARSEABLE | #UNPARSEABLE |  | #UNPARSEABLE | 6 | Rohan Kapoor |  |  |  | Green | SIT on STAGING Set Up | Not Started | 0% | 2026-07-07 | 2026-07-09 |  |  |  |  | 3d | 189 | 62 | [8 empty] | Solvara Integration Team, Zycus Integration Team
#UNPARSEABLE | #UNPARSEABLE | #UNPARSEABLE |  | #UNPARSEABLE | 6 | Rohan Kapoor |  |  |  | Green | Sign off on SIT | Not Started | 0% | 2026-07-09 | 2026-07-09 |  |  |  |  | 1d | 191FF | 66 | [8 empty] | Solvara Integration Team
#UNPARSEABLE | #UNPARSEABLE | #UNPARSEABLE |  | #UNPARSEABLE | 3 | Rohan Kapoor |  |  |  | Red | eProc Integration: Completion of Design | Not Started | 0% | 2026-06-24 | 2026-06-24 |  |  |  |  | 0 | 181 | 77
#UNPARSEABLE | #UNPARSEABLE | #UNPARSEABLE |  | #UNPARSEABLE | 3 | Rohan Kapoor |  |  |  | Green | eProc Integration: Completion of Development and Testing | Not Started | 0% | 2026-07-09 | 2026-07-09 |  |  |  |  | 0 | 186 | 66
#UNPARSEABLE | #UNPARSEABLE | #UNPARSEABLE |  | #UNPARSEABLE | 3 | Rohan Kapoor |  |  |  | Green | eProc Integration: Completion of SIT | Not Started | 0% | 2026-07-09 | 2026-07-09 |  |  |  |  | 0 | 190 | 66
#UNPARSEABLE | #UNPARSEABLE | #UNPARSEABLE |  | #UNPARSEABLE | 2 | Rohan Kapoor |  |  |  | Yellow | Integrations ASN | In Progress | 42% | 2026-06-23 | 2026-07-14 |  |  |  |  | 16d |  | 63
#UNPARSEABLE | #UNPARSEABLE | #UNPARSEABLE |  | #UNPARSEABLE | 3 | Rohan Kapoor |  |  |  | Yellow | eProc Integration with SAP for Purchase order | In Progress | 42% | 2026-06-23 | 2026-07-14 |  |  |  |  | 16d |  | 63
#UNPARSEABLE | #UNPARSEABLE | #UNPARSEABLE |  | #UNPARSEABLE | 4 | Rohan Kapoor |  |  |  | Red | Integration Design | In Progress | 83% | 2026-06-23 | 2026-06-25 |  |  |  |  | 3d |  | 76
#UNPARSEABLE | #UNPARSEABLE | #UNPARSEABLE |  | #UNPARSEABLE | 5 | Rohan Kapoor |  |  |  | Green | Mapping activity for Integration | Completed | 100% | 2026-06-23 | 2026-06-23 |  |  |  |  | 1d | 182 | 24 | [8 empty] | Solvara Integration Team, Zycus Integration Specialist
#UNPARSEABLE | #UNPARSEABLE | #UNPARSEABLE |  | #UNPARSEABLE | 5 | Rohan Kapoor |  |  |  | Green | Share TDD for interface | Completed | 100% | 2026-06-24 | 2026-06-24 |  |  |  |  | 1d | 199 | 24 | [8 empty] | Zycus Integration Lead
#UNPARSEABLE | #UNPARSEABLE | #UNPARSEABLE |  | #UNPARSEABLE | 5 | Rohan Kapoor |  |  |  | Red | Review of TDD and share feedback with Zycus | In Progress | 50% | 2026-06-25 | 2026-06-25 |  |  |  |  | 1d | 200 | 66 | [8 empty] | Solvara Integration Team
#UNPARSEABLE | #UNPARSEABLE | #UNPARSEABLE |  | #UNPARSEABLE | 5 | Rohan Kapoor |  |  |  | Red | Sign off on TDD | Not Started | 0% | 2026-06-25 | 2026-06-25 |  |  |  |  | 0 | 201 | 66 | [8 empty] | Solvara Integration Team
#UNPARSEABLE | #UNPARSEABLE | #UNPARSEABLE |  | #UNPARSEABLE | 4 | Rohan Kapoor |  |  |  | Yellow | Development and Testing on STAGING Set Up | In Progress | 32% | 2026-06-26 | 2026-07-14 |  |  |  |  | 13d |  | 63
#UNPARSEABLE | #UNPARSEABLE | #UNPARSEABLE |  | #UNPARSEABLE | 5 | Rohan Kapoor |  |  |  | Yellow | Integration set up and development at Zycus | In Progress | 90% | 2026-06-26 | 2026-07-02 |  |  |  |  | 5d | 202 | 66 | [8 empty] | Zycus Integration Specialist
#UNPARSEABLE | #UNPARSEABLE | #UNPARSEABLE |  | #UNPARSEABLE | 5 | Rohan Kapoor |  |  |  | Red | Integration development at Solvara - as applicable | Not Started | 0% | 2026-06-26 | 2026-07-02 |  |  |  |  | 5d | 202 | 66 | [8 empty] | Solvara Integration Team
#UNPARSEABLE | #UNPARSEABLE | #UNPARSEABLE |  | #UNPARSEABLE | 5 | Rohan Kapoor |  |  |  | Green | Integration Unit Testing and Feedback Incorporation | Not Started | 0% | 2026-07-03 | 2026-07-03 |  |  |  |  | 1d | 204, 205 | 66 | [8 empty] | Zycus Integration Team
#UNPARSEABLE | #UNPARSEABLE | #UNPARSEABLE |  | #UNPARSEABLE | 5 | Rohan Kapoor |  |  |  | Green | Systems Integration Testing | Not Started | 0% | 2026-07-10 | 2026-07-14 |  |  |  |  | 3d |  | 63
#UNPARSEABLE | #UNPARSEABLE | #UNPARSEABLE |  | #UNPARSEABLE | 6 | Rohan Kapoor |  |  |  | Green | SIT on STAGING Set Up | Not Started | 0% | 2026-07-10 | 2026-07-14 |  |  |  |  | 3d | 206, 191 | 62 | [8 empty] | Solvara Integration Team, Zycus Integration Team
#UNPARSEABLE | #UNPARSEABLE | #UNPARSEABLE |  | #UNPARSEABLE | 6 | Rohan Kapoor |  |  |  | Green | Sign off on SIT | Not Started | 0% | 2026-07-14 | 2026-07-14 |  |  |  |  | 1d | 208FF | 63 | [8 empty] | Solvara Integration Team
#UNPARSEABLE | #UNPARSEABLE | #UNPARSEABLE |  | #UNPARSEABLE | 3 | Rohan Kapoor |  |  |  | Red | eProc Integration: Completion of Design | Not Started | 0% | 2026-06-25 | 2026-06-25 |  |  |  |  | 0 | 198 | 76
#UNPARSEABLE | #UNPARSEABLE | #UNPARSEABLE |  | #UNPARSEABLE | 3 | Rohan Kapoor |  |  |  | Green | eProc Integration: Completion of Development and Testing | Not Started | 0% | 2026-07-14 | 2026-07-14 |  |  |  |  | 0 | 203 | 63
#UNPARSEABLE | #UNPARSEABLE | #UNPARSEABLE |  | #UNPARSEABLE | 3 | Rohan Kapoor |  |  |  | Green | eProc Integration: Completion of SIT | Not Started | 0% | 2026-07-14 | 2026-07-14 |  |  |  |  | 0 | 207 | 63
#UNPARSEABLE | #UNPARSEABLE | #UNPARSEABLE |  | #UNPARSEABLE | 2 | Rohan Kapoor |  |  |  | Yellow | Integrations eInvoice | Not Started | 0% | 2026-07-01 | 2026-08-04 |  |  |  |  | 25d |  | 48
#UNPARSEABLE | #UNPARSEABLE | #UNPARSEABLE |  | #UNPARSEABLE | 3 | Rohan Kapoor |  |  |  | Yellow | eInvoice Integration | Not Started | 0% | 2026-07-01 | 2026-08-04 |  |  |  |  | 25d |  | 48
#UNPARSEABLE | #UNPARSEABLE | #UNPARSEABLE |  | #UNPARSEABLE | 4 | Rohan Kapoor |  |  |  | Red | Integration Design | Not Started | 0% | 2026-07-01 | 2026-07-06 |  |  |  |  | 4d |  | 69
#UNPARSEABLE | #UNPARSEABLE | #UNPARSEABLE |  | #UNPARSEABLE | 5 | Rohan Kapoor |  |  |  | Red | Mapping activity for Integration | Not Started | 0% | 2026-07-01 | 2026-07-01 |  |  |  |  | 1d | 276 | 69 | [8 empty] | Solvara Integration Team, Zycus Integration Specialist
#UNPARSEABLE | #UNPARSEABLE | #UNPARSEABLE |  | #UNPARSEABLE | 5 | Rohan Kapoor |  |  |  | Red | Share TDD for interface | Not Started | 0% | 2026-07-02 | 2026-07-02 |  |  |  |  | 1d | 216 | 69 | [8 empty] | Zycus Integration Lead
#UNPARSEABLE | #UNPARSEABLE | #UNPARSEABLE |  | #UNPARSEABLE | 5 | Rohan Kapoor |  |  |  | Green | Review of TDD and share feedback with Zycus | Not Started | 0% | 2026-07-03 | 2026-07-03 |  |  |  |  | 1d | 217 | 69 | [8 empty] | Solvara Integration Team
#UNPARSEABLE | #UNPARSEABLE | #UNPARSEABLE |  | #UNPARSEABLE | 5 | Rohan Kapoor |  |  |  | Green | Sign off on TDD | Not Started | 0% | 2026-07-06 | 2026-07-06 |  |  |  |  | 1d | 218 | 69 | [8 empty] | Solvara Integration Team
#UNPARSEABLE | #UNPARSEABLE | #UNPARSEABLE |  | #UNPARSEABLE | 4 | Rohan Kapoor |  |  |  | Green | Development and Testing on STAGING Set Up | Not Started | 0% | 2026-07-15 | 2026-08-04 |  |  |  |  | 15d |  | 48
#UNPARSEABLE | #UNPARSEABLE | #UNPARSEABLE |  | #UNPARSEABLE | 5 | Rohan Kapoor |  |  |  | Green | Integration set up and development at Zycus | Not Started | 0% | 2026-07-15 | 2026-07-21 |  |  |  |  | 5d | 280 | 47 | [8 empty] | Zycus Integration Specialist
#UNPARSEABLE | #UNPARSEABLE | #UNPARSEABLE |  | #UNPARSEABLE | 5 | Rohan Kapoor |  |  |  | Green | Integration development at Solvara - as applicable | Not Started | 0% | 2026-07-22 | 2026-07-28 |  |  |  |  | 5d | 221 | 47 | [8 empty] | Solvara Integration Team
#UNPARSEABLE | #UNPARSEABLE | #UNPARSEABLE |  | #UNPARSEABLE | 5 | Rohan Kapoor |  |  |  | Green | Integration Unit Testing and Feedback Incorporation | Not Started | 0% | 2026-07-29 | 2026-07-30 |  |  |  |  | 2d | 221, 222 | 47 | [8 empty] | Zycus Integration Team
#UNPARSEABLE | #UNPARSEABLE | #UNPARSEABLE |  | #UNPARSEABLE | 5 | Rohan Kapoor |  |  |  | Green | Systems Integration Testing | Not Started | 0% | 2026-07-31 | 2026-08-04 |  |  |  |  | 3d |  | 48
#UNPARSEABLE | #UNPARSEABLE | #UNPARSEABLE |  | #UNPARSEABLE | 6 | Rohan Kapoor |  |  |  | Green | SIT on STAGING Set Up | Not Started | 0% | 2026-07-31 | 2026-08-04 |  |  |  |  | 3d | 223 | 47 | [8 empty] | Solvara Integration Team, Zycus Integration Team
#UNPARSEABLE | #UNPARSEABLE | #UNPARSEABLE |  | #UNPARSEABLE | 6 | Rohan Kapoor |  |  |  | Green | Sign off on SIT | Not Started | 0% | 2026-08-04 | 2026-08-04 |  |  |  |  | 1d | 225FF | 48 | [8 empty] | Solvara Integration Team
#UNPARSEABLE | #UNPARSEABLE | #UNPARSEABLE |  | #UNPARSEABLE | 3 | Rohan Kapoor |  |  |  | Green | eInvoice Integration: Completion of Design | Not Started | 0% | 2026-07-06 | 2026-07-06 |  |  |  |  | 0 | 215 | 69
#UNPARSEABLE | #UNPARSEABLE | #UNPARSEABLE |  | #UNPARSEABLE | 3 | Rohan Kapoor |  |  |  | Green | eInvoice Integration: Completion of Development and Testing | Not Started | 0% | 2026-08-04 | 2026-08-04 |  |  |  |  | 0 | 220 | 48
#UNPARSEABLE | #UNPARSEABLE | #UNPARSEABLE |  | #UNPARSEABLE | 3 | Rohan Kapoor |  |  |  | Green | eInvoice Integration: Completion of SIT | Not Started | 0% | 2026-08-04 | 2026-08-04 |  |  |  |  | 0 | 224 | 48
#UNPARSEABLE | #UNPARSEABLE | #UNPARSEABLE |  | #UNPARSEABLE | 1 | Rohan Kapoor |  |  |  | Green | Contract Management with Basic Setup | In Progress | 3% | 2026-07-14 | 2026-08-07 |  |  |  |  | 19d |  | 45
#UNPARSEABLE | #UNPARSEABLE | #UNPARSEABLE |  | #UNPARSEABLE | 2 | Rohan Kapoor |  |  |  | Green | iContract Deployment (Repository + Authoring) | Not Started | 0% | 2026-07-22 | 2026-07-28 |  |  |  |  | 5d |  | 53
#UNPARSEABLE | #UNPARSEABLE | #UNPARSEABLE |  | #UNPARSEABLE | 3 | Rohan Kapoor |  |  |  | Green | Functional Configuration on STAGING set Up | Not Started | 0% | 2026-07-22 | 2026-07-28 |  |  |  |  | 5d |  | 53
#UNPARSEABLE | #UNPARSEABLE | #UNPARSEABLE |  | #UNPARSEABLE | 4 | Rohan Kapoor |  |  |  | Green | User Role Configuration | Not Started | 0% | 2026-07-22 | 2026-07-22 |  |  |  |  | 1d | 163 | 23 | [8 empty] | Zycus Product Specialist
#UNPARSEABLE | #UNPARSEABLE | #UNPARSEABLE |  | #UNPARSEABLE | 4 | Rohan Kapoor |  |  |  | Green | Admin Settings Configuration | Not Started | 0% | 2026-07-22 | 2026-07-22 |  |  |  |  | 0 | 233 | 57 | [8 empty] | Zycus Product Specialist
#UNPARSEABLE | #UNPARSEABLE | #UNPARSEABLE |  | #UNPARSEABLE | 4 | Rohan Kapoor |  |  |  | Green | Readiness for Pre-UAT | Not Started | 0% | 2026-07-23 | 2026-07-23 |  |  |  |  | 1d | 233 | 23 | [8 empty] | Zycus Product Specialist
#UNPARSEABLE | #UNPARSEABLE | #UNPARSEABLE |  | #UNPARSEABLE | 4 | Rohan Kapoor |  |  |  | Green | Pre-UAT | Not Started | 0% | 2026-07-24 | 2026-07-28 |  |  |  |  | 3d |  | 53
#UNPARSEABLE | #UNPARSEABLE | #UNPARSEABLE |  | #UNPARSEABLE | 5 | Rohan Kapoor |  |  |  | Green | Pre-UAT - Provide End to end walkthrough of configured iContract to Solvara | Not Started | 0% | 2026-07-24 | 2026-07-24 |  |  |  |  | 1d | 235 | 16 | [8 empty] | Solvara Core Project Team, Zycus Consultant, Zycus Product Specialist
#UNPARSEABLE | #UNPARSEABLE | #UNPARSEABLE |  | #UNPARSEABLE | 5 | Rohan Kapoor |  |  |  | Green | Provide feedback - if any for iContract configuration | Not Started | 0% | 2026-07-27 | 2026-07-28 |  |  |  |  | 2d | 237 | 13 | [8 empty] | Solvara Project Team
#UNPARSEABLE | #UNPARSEABLE | #UNPARSEABLE |  | #UNPARSEABLE | 5 | Rohan Kapoor |  |  |  | Green | Zycus to incorporate feedback - as applicable and share final version of Implementation Approach Document [IAD] | Not Started | 0% | 2026-07-28 | 2026-07-28 |  |  |  |  | 1d | 238SS +1d | 23 | [8 empty] | Zycus Consultant, Zycus Product Specialist
#UNPARSEABLE | #UNPARSEABLE | #UNPARSEABLE |  | #UNPARSEABLE | 5 | Rohan Kapoor |  |  |  | Green | Sign off on Pre-UAT and final version of IAD sign off | Not Started | 0% | 2026-07-28 | 2026-07-28 |  |  |  |  | 0 | 239 | 21 | [8 empty] | Solvara Project Manager
#UNPARSEABLE | #UNPARSEABLE | #UNPARSEABLE |  | #UNPARSEABLE | 2 | Rohan Kapoor |  |  |  | Green | iContract: Conclude Functional Configuration | Not Started | 0% | 2026-07-29 | 2026-08-04 |  |  |  |  | 5d | 240 | 48
#UNPARSEABLE | #UNPARSEABLE | #UNPARSEABLE |  | #UNPARSEABLE | 2 | Rohan Kapoor |  |  |  | Green | Historical contracts Bulk Upload [up to 25,000 contracts] | In Progress | 5% | 2026-07-14 | 2026-08-07 |  |  |  |  | 19d |  | 45
#UNPARSEABLE | #UNPARSEABLE | #UNPARSEABLE |  | #UNPARSEABLE | 3 | Rohan Kapoor |  |  |  | Green | Zycus to provide walkthrough of shared template to Solvara | In Progress | 40% | 2026-07-14 | 2026-07-14 |  |  |  |  | 1d | 240FS -11d | 41 | [8 empty] | Solvara Project Team, Zycus Product Specialist
#UNPARSEABLE | #UNPARSEABLE | #UNPARSEABLE |  | #UNPARSEABLE | 3 | Rohan Kapoor |  |  |  | Green | Solvara to provide historical contracts details for Bulk Upload | In Progress | 40% | 2026-07-15 | 2026-07-16 |  |  |  |  | 2d | 243 | 43 | [8 empty] | Solvara IT Team
#UNPARSEABLE | #UNPARSEABLE | #UNPARSEABLE |  | #UNPARSEABLE | 3 | Rohan Kapoor |  |  |  | Green | Zycus to review shared details and provide feedback - if any | Not Started | 0% | 2026-07-15 | 2026-07-16 |  |  |  |  | 2d | 244FF | 43 | [8 empty] | Zycus Product Specialist
#UNPARSEABLE | #UNPARSEABLE | #UNPARSEABLE |  | #UNPARSEABLE | 3 | Rohan Kapoor |  |  |  | Green | Solvara to incorporate feedback and provide revised final details of historical contracts for bulk upload into iContract | Not Started | 0% | 2026-07-17 | 2026-07-20 |  |  |  |  | 2d | 245 | 45 | [8 empty] | Solvara IT Team
#UNPARSEABLE | #UNPARSEABLE | #UNPARSEABLE |  | #UNPARSEABLE | 3 | Rohan Kapoor |  |  |  | Green | Zycus to ensure supplier details availability in STAGING | Not Started | 0% | 2026-07-17 | 2026-07-20 |  |  |  |  | 2d | 246FF, 266 | 45 | [8 empty] | Zycus Product Specialist
#UNPARSEABLE | #UNPARSEABLE | #UNPARSEABLE |  | #UNPARSEABLE | 3 | Rohan Kapoor |  |  |  | Green | Zycus to bulk upload historical contracts details in STGAING [10 contracts for each Type/Subtype] | Not Started | 0% | 2026-07-21 | 2026-07-22 |  |  |  |  | 2d | 246, 247 | 45 | [8 empty] | Zycus Product Specialist
#UNPARSEABLE | #UNPARSEABLE | #UNPARSEABLE |  | #UNPARSEABLE | 3 | Rohan Kapoor |  |  |  | Green | Solvara to review uploaded details and provide go ahead for bulk upload into PRODUCTION | Not Started | 0% | 2026-07-23 | 2026-07-24 |  |  |  |  | 2d | 248, 269 | 45 | [8 empty] | Solvara Project Team
#UNPARSEABLE | #UNPARSEABLE | #UNPARSEABLE |  | #UNPARSEABLE | 3 | Rohan Kapoor |  |  |  | Green | Zycus to bulk upload historical contracts details in Production | Not Started | 0% | 2026-07-27 | 2026-08-07 |  |  |  |  | 10d | 249 | 45 | [8 empty] | Zycus Product Specialist
#UNPARSEABLE | #UNPARSEABLE | #UNPARSEABLE |  | #UNPARSEABLE | 1 | Rohan Kapoor |  |  |  | Red | Supplier Information Management with Integration | In Progress | 12% | 2026-06-12 | 2026-08-11 |  |  |  |  | 43d |  | 43
#UNPARSEABLE | #UNPARSEABLE | #UNPARSEABLE |  | #UNPARSEABLE | 2 | Rohan Kapoor |  |  |  | Red | iSupplier Deployment | In Progress | 13% | 2026-06-12 | 2026-08-11 |  |  |  |  | 43d |  | 43
#UNPARSEABLE | #UNPARSEABLE | #UNPARSEABLE |  | #UNPARSEABLE | 3 | Rohan Kapoor |  |  |  | Red | Design & Development on STAGING Set UP | In Progress | 13% | 2026-06-12 | 2026-08-11 |  |  |  |  | 43d |  | 43
#UNPARSEABLE | #UNPARSEABLE | #UNPARSEABLE |  | #UNPARSEABLE | 4 | Rohan Kapoor |  |  |  | Green | Users,Roles,Workflow & View Definition Configuration | Not Started | 0% | 2026-07-22 | 2026-07-22 |  |  |  |  | 1d |  | 23
#UNPARSEABLE | #UNPARSEABLE | #UNPARSEABLE |  | #UNPARSEABLE | 5 | Rohan Kapoor |  |  |  | Green | Configure User Roles, View Definition and Workflow as per IAD | Not Started | 0% | 2026-07-22 | 2026-07-22 |  |  |  |  | 1d | 163 | 42 | [8 empty] | Zycus Product Specialist
#UNPARSEABLE | #UNPARSEABLE | #UNPARSEABLE |  | #UNPARSEABLE | 5 | Rohan Kapoor |  |  |  | Green | Solvara to provide feedback | Not Started | 0% | 2026-07-22 | 2026-07-22 |  |  |  |  | 0 | 255 | 42 | [8 empty] | Solvara Core Project Team, Solvara Subject Matter Expert
#UNPARSEABLE | #UNPARSEABLE | #UNPARSEABLE |  | #UNPARSEABLE | 4 | Rohan Kapoor |  |  |  | Red | Pre-UAT on STAGING Set UP | In Progress | 5% | 2026-06-12 | 2026-07-22 |  |  |  |  | 29d |  | 57
#UNPARSEABLE | #UNPARSEABLE | #UNPARSEABLE |  | #UNPARSEABLE | 5 | Rohan Kapoor |  |  |  | Green | Pre-UAT - Provide End to end walkthrough of configured iSupplier to Solvara | Not Started | 0% | 2026-07-22 | 2026-07-22 |  |  |  |  | 0 | 254 | 23 | [8 empty] | Zycus Consultant, Zycus Product Specialist
#UNPARSEABLE | #UNPARSEABLE | #UNPARSEABLE |  | #UNPARSEABLE | 5 | Rohan Kapoor |  |  |  | Green | Provide feedback - if any for iSupplier configuration | Not Started | 0% | 2026-07-22 | 2026-07-22 |  |  |  |  | 0 | 258 | 23 | [8 empty] | Solvara Project Team
#UNPARSEABLE | #UNPARSEABLE | #UNPARSEABLE |  | #UNPARSEABLE | 5 | Rohan Kapoor |  |  |  | Green | Zycus to incorporate feedback - as applicable and share final version of Implementation Approach Document [IAD] | Not Started | 0% | 2026-07-22 | 2026-07-22 |  |  |  |  | 0 | 258, 259 | 22 | [8 empty] | Zycus Consultant
#UNPARSEABLE | #UNPARSEABLE | #UNPARSEABLE |  | #UNPARSEABLE | 5 | Rohan Kapoor |  |  |  | Green | Sign off on Pre-UAT and final version of IAD | Not Started | 0% | 2026-07-22 | 2026-07-22 |  |  |  |  | 0 | 260 | 21 | [8 empty] | Solvara Project Manager, Zycus Project Manager
#UNPARSEABLE | #UNPARSEABLE | #UNPARSEABLE |  | #UNPARSEABLE | 5 | Rohan Kapoor |  |  |  | Red | Supplier Bulk Upload on STAGING | In Progress | 5% | 2026-06-12 | 2026-07-15 |  |  |  |  | 24d |  | 62
#UNPARSEABLE | #UNPARSEABLE | #UNPARSEABLE |  | #UNPARSEABLE | 6 | Rohan Kapoor |  |  |  | Red | Solvara to provide supplier bulk upload data in the template provided by Zycus from Solvara's Staging environment | In Progress | 50% | 2026-06-12 | 2026-06-12 |  |  |  |  | 1d | 260FS -29d | 45 | [8 empty] | Solvara IT Project Manager, Solvara IT Team, Solvara Project Manager
#UNPARSEABLE | #UNPARSEABLE | #UNPARSEABLE |  | #UNPARSEABLE | 6 | Rohan Kapoor |  |  |  | Red | Zycus to review the files and provide feedback | In Progress | 50% | 2026-06-15 | 2026-06-15 |  |  |  |  | 1d | 263 | 45 | [8 empty] | Zycus Product Specialist
#UNPARSEABLE | #UNPARSEABLE | #UNPARSEABLE |  | #UNPARSEABLE | 6 | Rohan Kapoor |  |  |  | Red | Solvara to provide updated bulk upload data | Not Started | 0% | 2026-06-23 | 2026-06-24 |  |  |  |  | 2d | 264FS +5d | 45 | [8 empty] | Solvara IT Project Manager, Solvara IT Team, Solvara Project Manager
#UNPARSEABLE | #UNPARSEABLE | #UNPARSEABLE |  | #UNPARSEABLE | 6 | Rohan Kapoor |  |  |  | Red | Zycus to bulk upload supplier data on STAGING setup | Not Started | 0% | 2026-06-25 | 2026-06-26 |  |  |  |  | 2d | 265 | 45 | [8 empty] | Zycus Product Specialist
#UNPARSEABLE | #UNPARSEABLE | #UNPARSEABLE |  | #UNPARSEABLE | 6 | Rohan Kapoor |  |  |  | Red | Solvara to review bulk uploaded data | Not Started | 0% | 2026-06-29 | 2026-07-01 |  |  |  |  | 3d | 266 | 49 | [8 empty] | Solvara Core Project Team
#UNPARSEABLE | #UNPARSEABLE | #UNPARSEABLE |  | #UNPARSEABLE | 6 | Rohan Kapoor |  |  |  | Red | Solvara to sign off on supplier bulk upload | Not Started | 0% | 2026-07-01 | 2026-07-01 |  |  |  |  | 1d | 267FF | 50 | [8 empty] | Solvara Project Manager
#UNPARSEABLE | #UNPARSEABLE | #UNPARSEABLE |  | #UNPARSEABLE | 6 | Rohan Kapoor |  |  |  | Yellow | Solvara Prod migration Supplier | Not Started | 0% | 2026-07-02 | 2026-07-15 |  |  |  |  | 10d | 268 | 50 | [8 empty] | Zycus Product Specialist
#UNPARSEABLE | #UNPARSEABLE | #UNPARSEABLE |  | #UNPARSEABLE | 4 | Rohan Kapoor |  |  |  | Green | Integration iSupplier | In Progress | 38% | 2026-06-25 | 2026-07-16 |  |  |  |  | 16d |  | 61
#UNPARSEABLE | #UNPARSEABLE | #UNPARSEABLE |  | #UNPARSEABLE | 5 | Rohan Kapoor |  |  |  | Green | iSupplier Integration | In Progress | 38% | 2026-06-25 | 2026-07-16 |  |  |  |  | 16d |  | 61
#UNPARSEABLE | #UNPARSEABLE | #UNPARSEABLE |  | #UNPARSEABLE | 6 | Rohan Kapoor |  |  |  | Red | Integration Design | In Progress | 63% | 2026-06-25 | 2026-06-30 |  |  |  |  | 4d |  | 73
#UNPARSEABLE | #UNPARSEABLE | #UNPARSEABLE |  | #UNPARSEABLE | 7 | Rohan Kapoor |  |  |  | Green | Mapping activity for Integration | Completed | 100% | 2026-06-25 | 2026-06-25 |  |  |  |  | 1d | 200 | 24 | [8 empty] | Solvara Integration Team, Zycus Integration Specialist
#UNPARSEABLE | #UNPARSEABLE | #UNPARSEABLE |  | #UNPARSEABLE | 7 | Rohan Kapoor |  |  |  | Green | Share TDD for interface | Completed | 100% | 2026-06-26 | 2026-06-26 |  |  |  |  | 1d | 273 | 27 | [8 empty] | Zycus Integration Lead
#UNPARSEABLE | #UNPARSEABLE | #UNPARSEABLE |  | #UNPARSEABLE | 7 | Rohan Kapoor |  |  |  | Red | Review of TDD and share feedback with Zycus | In Progress | 50% | 2026-06-29 | 2026-06-29 |  |  |  |  | 1d | 274 | 24 | [8 empty] | Solvara Integration Team
#UNPARSEABLE | #UNPARSEABLE | #UNPARSEABLE |  | #UNPARSEABLE | 7 | Rohan Kapoor |  |  |  | Red | Sign off on TDD | Not Started | 0% | 2026-06-30 | 2026-06-30 |  |  |  |  | 1d | 275 | 27 | [8 empty] | Solvara Integration Team
#UNPARSEABLE | #UNPARSEABLE | #UNPARSEABLE |  | #UNPARSEABLE | 6 | Rohan Kapoor |  |  |  | Green | Development and Testing on STAGING Set Up | In Progress | 29% | 2026-07-01 | 2026-07-16 |  |  |  |  | 12d |  | 61
#UNPARSEABLE | #UNPARSEABLE | #UNPARSEABLE |  | #UNPARSEABLE | 7 | Rohan Kapoor |  |  |  | Green | Integration set up and development at Zycus | In Progress | 80% | 2026-07-06 | 2026-07-10 |  |  |  |  | 5d | 276FS +3d | 24 | [8 empty] | Zycus Integration Specialist
#UNPARSEABLE | #UNPARSEABLE | #UNPARSEABLE |  | #UNPARSEABLE | 7 | Rohan Kapoor |  |  |  | Red | Integration development at Solvara - as applicable | Not Started | 0% | 2026-07-01 | 2026-07-07 |  |  |  |  | 5d | 276 | 24 | [8 empty] | Solvara Integration Team
#UNPARSEABLE | #UNPARSEABLE | #UNPARSEABLE |  | #UNPARSEABLE | 7 | Rohan Kapoor |  |  |  | Green | Integration Unit Testing and Feedback Incorporation | Not Started | 0% | 2026-07-13 | 2026-07-14 |  |  |  |  | 2d | 278, 279 | 24 | [8 empty] | Zycus Integration Team
#UNPARSEABLE | #UNPARSEABLE | #UNPARSEABLE |  | #UNPARSEABLE | 7 | Rohan Kapoor |  |  |  | Green | Systems Integration Testing | Not Started | 0% | 2026-07-15 | 2026-07-16 |  |  |  |  | 2d |  | 61
#UNPARSEABLE | #UNPARSEABLE | #UNPARSEABLE |  | #UNPARSEABLE | 8 | Rohan Kapoor |  |  |  | Green | SIT on STAGING Set Up | Not Started | 0% | 2026-07-15 | 2026-07-16 |  |  |  |  | 2d | 280 | 23 | [8 empty] | Solvara Integration Team, Zycus Integration Team
#UNPARSEABLE | #UNPARSEABLE | #UNPARSEABLE |  | #UNPARSEABLE | 8 | Rohan Kapoor |  |  |  | Green | Sign off on SIT | Not Started | 0% | 2026-07-16 | 2026-07-16 |  |  |  |  | 1d | 282FF | 23 | [8 empty] | Solvara Integration Team
#UNPARSEABLE | #UNPARSEABLE | #UNPARSEABLE |  | #UNPARSEABLE | 5 | Rohan Kapoor |  |  |  | Red | eInvoice Integration: Completion of Design | Not Started | 0% | 2026-06-30 | 2026-06-30 |  |  |  |  | 0 | 272 | 73
#UNPARSEABLE | #UNPARSEABLE | #UNPARSEABLE |  | #UNPARSEABLE | 5 | Rohan Kapoor |  |  |  | Green | eInvoice Integration: Completion of Development and Testing | Not Started | 0% | 2026-07-16 | 2026-07-16 |  |  |  |  | 0 | 277 | 61
#UNPARSEABLE | #UNPARSEABLE | #UNPARSEABLE |  | #UNPARSEABLE | 5 | Rohan Kapoor |  |  |  | Green | eInvoice Integration: Completion of SIT | Not Started | 0% | 2026-07-16 | 2026-07-16 |  |  |  |  | 0 | 281 | 61
#UNPARSEABLE | #UNPARSEABLE | #UNPARSEABLE |  | #UNPARSEABLE | 4 | Rohan Kapoor |  |  |  | Green | Integration iSupplier - Exiger | Not Started | 0% | 2026-07-23 | 2026-08-11 |  |  |  |  | 14d |  | 43
#UNPARSEABLE | #UNPARSEABLE | #UNPARSEABLE |  | #UNPARSEABLE | 5 | Rohan Kapoor |  |  |  | Green | iSupplier Integration | Not Started | 0% | 2026-07-23 | 2026-08-11 |  |  |  |  | 14d |  | 43
#UNPARSEABLE | #UNPARSEABLE | #UNPARSEABLE |  | #UNPARSEABLE | 6 | Rohan Kapoor |  |  |  | Green | Integration Design | Not Started | 0% | 2026-07-23 | 2026-07-28 |  |  |  |  | 4d |  | 53
#UNPARSEABLE | #UNPARSEABLE | #UNPARSEABLE |  | #UNPARSEABLE | 7 | Rohan Kapoor |  |  |  | Green | Mapping activity for Integration | Not Started | 0% | 2026-07-23 | 2026-07-23 |  |  |  |  | 1d | 256 | 42 | [8 empty] | Solvara Integration Team, Zycus Integration Specialist
#UNPARSEABLE | #UNPARSEABLE | #UNPARSEABLE |  | #UNPARSEABLE | 7 | Rohan Kapoor |  |  |  | Green | Share TDD for interface | Not Started | 0% | 2026-07-24 | 2026-07-24 |  |  |  |  | 1d | 290 | 42 | [8 empty] | Zycus Integration Lead
#UNPARSEABLE | #UNPARSEABLE | #UNPARSEABLE |  | #UNPARSEABLE | 7 | Rohan Kapoor |  |  |  | Green | Review of TDD and share feedback with Zycus | Not Started | 0% | 2026-07-27 | 2026-07-27 |  |  |  |  | 1d | 291 | 42 | [8 empty] | Solvara Integration Team
#UNPARSEABLE | #UNPARSEABLE | #UNPARSEABLE |  | #UNPARSEABLE | 7 | Rohan Kapoor |  |  |  | Green | Sign off on TDD | Not Started | 0% | 2026-07-28 | 2026-07-28 |  |  |  |  | 1d | 292 | 42 | [8 empty] | Solvara Integration Team
#UNPARSEABLE | #UNPARSEABLE | #UNPARSEABLE |  | #UNPARSEABLE | 6 | Rohan Kapoor |  |  |  | Green | Development and Testing on STAGING Set Up | Not Started | 0% | 2026-07-29 | 2026-08-11 |  |  |  |  | 10d |  | 43
#UNPARSEABLE | #UNPARSEABLE | #UNPARSEABLE |  | #UNPARSEABLE | 7 | Rohan Kapoor |  |  |  | Green | Integration set up and development at Zycus | Not Started | 0% | 2026-07-29 | 2026-08-04 |  |  |  |  | 5d | 293 | 42 | [8 empty] | Zycus Integration Specialist
#UNPARSEABLE | #UNPARSEABLE | #UNPARSEABLE |  | #UNPARSEABLE | 7 | Rohan Kapoor |  |  |  | Green | Integration development at Solvara - as applicable | Not Started | 0% | 2026-07-29 | 2026-08-04 |  |  |  |  | 5d | 293 | 42 | [8 empty] | Solvara Integration Team
#UNPARSEABLE | #UNPARSEABLE | #UNPARSEABLE |  | #UNPARSEABLE | 7 | Rohan Kapoor |  |  |  | Green | Integration Unit Testing and Feedback Incorporation | Not Started | 0% | 2026-08-05 | 2026-08-06 |  |  |  |  | 2d | 295, 296 | 42 | [8 empty] | Zycus Integration Team
#UNPARSEABLE | #UNPARSEABLE | #UNPARSEABLE |  | #UNPARSEABLE | 7 | Rohan Kapoor |  |  |  | Green | Systems Integration Testing | Not Started | 0% | 2026-08-07 | 2026-08-11 |  |  |  |  | 3d |  | 43
#UNPARSEABLE | #UNPARSEABLE | #UNPARSEABLE |  | #UNPARSEABLE | 8 | Rohan Kapoor |  |  |  | Green | SIT on STAGING Set Up | Not Started | 0% | 2026-08-07 | 2026-08-11 |  |  |  |  | 3d | 297 | 42 | [8 empty] | Solvara Integration Team, Zycus Integration Team
#UNPARSEABLE | #UNPARSEABLE | #UNPARSEABLE |  | #UNPARSEABLE | 8 | Rohan Kapoor |  |  |  | Green | Sign off on SIT | Not Started | 0% | 2026-08-11 | 2026-08-11 |  |  |  |  | 1d | 299FF | 43 | [8 empty] | Solvara Integration Team
#UNPARSEABLE | #UNPARSEABLE | #UNPARSEABLE |  | #UNPARSEABLE | 5 | Rohan Kapoor |  |  |  | Green | eInvoice Integration: Completion of Design | Not Started | 0% | 2026-07-28 | 2026-07-28 |  |  |  |  | 0 | 289 | 53
#UNPARSEABLE | #UNPARSEABLE | #UNPARSEABLE |  | #UNPARSEABLE | 5 | Rohan Kapoor |  |  |  | Green | eInvoice Integration: Completion of Development and Testing | Not Started | 0% | 2026-08-11 | 2026-08-11 |  |  |  |  | 0 | 294 | 43
#UNPARSEABLE | #UNPARSEABLE | #UNPARSEABLE |  | #UNPARSEABLE | 5 | Rohan Kapoor |  |  |  | Green | eInvoice Integration: Completion of SIT | Not Started | 0% | 2026-08-11 | 2026-08-11 |  |  |  |  | 0 | 298 | 43
#UNPARSEABLE | #UNPARSEABLE | #UNPARSEABLE |  | #UNPARSEABLE | 2 | Rohan Kapoor |  |  |  | Green | iSupplier: Conclude Functional Configuration | Not Started | 0% | 2026-07-22 | 2026-07-22 |  |  |  |  | 0 | 257 | 57
#UNPARSEABLE | #UNPARSEABLE | #UNPARSEABLE |  | #UNPARSEABLE | 2 | Rohan Kapoor |  |  |  | Green | Value KPI Report creation on Staging | Not Started | 0% | 2026-07-23 | 2026-07-24 |  |  |  |  | 2d | 261 | 51 | [8 empty] | Solvara Project Group, Zycus Product Specialist, Zycus Project Manager
#UNPARSEABLE | #UNPARSEABLE | #UNPARSEABLE |  | #UNPARSEABLE | 2 | Rohan Kapoor |  |  |  | Green | Value KPI Report demo on Staging | Not Started | 0% | 2026-07-27 | 2026-07-28 |  |  |  |  | 2d | 305 | 51 | [8 empty] | Solvara Project Group, Zycus Product Specialist, Zycus Project Manager
#UNPARSEABLE | #UNPARSEABLE | #UNPARSEABLE |  | #UNPARSEABLE | 1 | Rohan Kapoor |  |  |  | Green | iSource Configuration | Not Started | 0% | 2026-07-22 | 2026-08-06 |  |  |  |  | 12d |  | 46
#UNPARSEABLE | #UNPARSEABLE | #UNPARSEABLE |  | #UNPARSEABLE | 2 | Rohan Kapoor |  |  |  | Green | iSource Deployment | Not Started | 0% | 2026-07-22 | 2026-08-06 |  |  |  |  | 12d |  | 46
#UNPARSEABLE | #UNPARSEABLE | #UNPARSEABLE |  | #UNPARSEABLE | 3 | Rohan Kapoor |  |  |  | Green | Functional Configuration Finalization on STAGING set Up | Not Started | 0% | 2026-07-22 | 2026-08-06 |  |  |  |  | 12d |  | 46
#UNPARSEABLE | #UNPARSEABLE | #UNPARSEABLE |  | #UNPARSEABLE | 4 | Rohan Kapoor |  |  |  | Green | User Roles configuration | Not Started | 0% | 2026-07-22 | 2026-07-22 |  |  |  |  | 1d | 163 | 0 | TRUE | [7 empty] | Zycus Product Specialist
#UNPARSEABLE | #UNPARSEABLE | #UNPARSEABLE |  | #UNPARSEABLE | 4 | Rohan Kapoor |  |  |  | Green | Admin settings configuration | Not Started | 0% | 2026-07-23 | 2026-07-24 |  |  |  |  | 2d | 310 | 0 | TRUE | [7 empty] | Zycus Product Specialist
#UNPARSEABLE | #UNPARSEABLE | #UNPARSEABLE |  | #UNPARSEABLE | 4 | Rohan Kapoor |  |  |  | Green | Readiness for Pre-UAT | Not Started | 0% | 2026-07-27 | 2026-07-28 |  |  |  |  | 2d | 311 | 0 | TRUE | [7 empty] | Zycus Product Specialist
#UNPARSEABLE | #UNPARSEABLE | #UNPARSEABLE |  | #UNPARSEABLE | 4 | Rohan Kapoor |  |  |  | Green | Pre-UAT on STAGING | Not Started | 0% | 2026-07-29 | 2026-08-06 |  |  |  |  | 7d |  | 46
#UNPARSEABLE | #UNPARSEABLE | #UNPARSEABLE |  | #UNPARSEABLE | 5 | Rohan Kapoor |  |  |  | Green | Pre-UAT - Provide End to end walkthrough of configured iSource to the Customer | Not Started | 0% | 2026-07-29 | 2026-07-30 |  |  |  |  | 2d | 312 | 0 | TRUE | [7 empty] | Zycus Consultant, Zycus Product Specialist
#UNPARSEABLE | #UNPARSEABLE | #UNPARSEABLE |  | #UNPARSEABLE | 5 | Rohan Kapoor |  |  |  | Green | Provide feedback - if any for iSource configuration | Not Started | 0% | 2026-07-31 | 2026-08-04 |  |  |  |  | 3d | 314 | 0 | TRUE | [7 empty] | Solvara Project Manager
#UNPARSEABLE | #UNPARSEABLE | #UNPARSEABLE |  | #UNPARSEABLE | 5 | Rohan Kapoor |  |  |  | Green | Zycus to incorporate feedback - as applicable and share final version of Implementation Approach Document [IAD] | Not Started | 0% | 2026-08-05 | 2026-08-06 |  |  |  |  | 2d | 314, 315 | 0 | TRUE | [7 empty] | Zycus Consultant, Zycus Product Specialist
#UNPARSEABLE | #UNPARSEABLE | #UNPARSEABLE |  | #UNPARSEABLE | 5 | Rohan Kapoor |  |  |  | Green | Sign off on Pre-UAT and final version of IAD | Not Started | 0% | 2026-08-06 | 2026-08-06 |  |  |  |  | 0 | 316 | 0 | TRUE | [7 empty] | Solvara Project Manager
#UNPARSEABLE | #UNPARSEABLE | #UNPARSEABLE |  | #UNPARSEABLE | 2 | Rohan Kapoor |  |  |  | Green | iSource : Conclude Functional Configuration | Not Started | 0% | 2026-08-06 | 2026-08-06 |  |  |  |  | 0 | 317 | 23
#UNPARSEABLE | #UNPARSEABLE | #UNPARSEABLE |  | #UNPARSEABLE | 1 | Rohan Kapoor |  |  |  | Green | Merlin Intake Configuration | Not Started | 0% | 2026-07-22 | 2026-08-05 |  |  |  |  | 11d |  | 47
#UNPARSEABLE | #UNPARSEABLE | #UNPARSEABLE |  | #UNPARSEABLE | 2 | Rohan Kapoor |  |  |  | Green | Merlin intake Deployment | Not Started | 0% | 2026-07-22 | 2026-08-05 |  |  |  |  | 11d |  | 47
#UNPARSEABLE | #UNPARSEABLE | #UNPARSEABLE |  | #UNPARSEABLE | 3 | Rohan Kapoor |  |  |  | Green | Functional Configuration Finalization on STAGING set Up | Not Started | 0% | 2026-07-22 | 2026-08-05 |  |  |  |  | 11d |  | 47
#UNPARSEABLE | #UNPARSEABLE | #UNPARSEABLE |  | #UNPARSEABLE | 4 | Rohan Kapoor |  |  |  | Green | User Roles configuration | Not Started | 0% | 2026-07-22 | 2026-07-22 |  |  |  |  | 1d | 163 | 4 | [8 empty] | Zycus Product Specialist
#UNPARSEABLE | #UNPARSEABLE | #UNPARSEABLE |  | #UNPARSEABLE | 4 | Rohan Kapoor |  |  |  | Green | Admin settings configuration | Not Started | 0% | 2026-07-23 | 2026-07-24 |  |  |  |  | 2d | 322 | 4 | [8 empty] | Zycus Product Specialist
#UNPARSEABLE | #UNPARSEABLE | #UNPARSEABLE |  | #UNPARSEABLE | 4 | Rohan Kapoor |  |  |  | Green | Readiness for Pre-UAT | Not Started | 0% | 2026-07-27 | 2026-07-28 |  |  |  |  | 2d | 323 | 4 | [8 empty] | Zycus Product Specialist
#UNPARSEABLE | #UNPARSEABLE | #UNPARSEABLE |  | #UNPARSEABLE | 4 | Rohan Kapoor |  |  |  | Green | Pre-UAT on STAGING | Not Started | 0% | 2026-07-29 | 2026-08-05 |  |  |  |  | 6d |  | 47
#UNPARSEABLE | #UNPARSEABLE | #UNPARSEABLE |  | #UNPARSEABLE | 5 | Rohan Kapoor |  |  |  | Green | Pre-UAT - Provide End to end walkthrough of configured Merlin Intake to the Customer | Not Started | 0% | 2026-07-29 | 2026-07-30 |  |  |  |  | 2d | 324 | 4 | [8 empty] | Zycus Consultant, Zycus Product Specialist
#UNPARSEABLE | #UNPARSEABLE | #UNPARSEABLE |  | #UNPARSEABLE | 5 | Rohan Kapoor |  |  |  | Green | Provide feedback - if any for Merlin Intake configuration | Not Started | 0% | 2026-07-31 | 2026-08-03 |  |  |  |  | 2d | 326 | 4 | [8 empty] | Solvara Project Manager
#UNPARSEABLE | #UNPARSEABLE | #UNPARSEABLE |  | #UNPARSEABLE | 5 | Rohan Kapoor |  |  |  | Green | Zycus to incorporate feedback - as applicable and share final version of Implementation Approach Document [IAD] | Not Started | 0% | 2026-08-04 | 2026-08-05 |  |  |  |  | 2d | 326, 327 | 4 | [8 empty] | Zycus Consultant, Zycus Product Specialist
#UNPARSEABLE | #UNPARSEABLE | #UNPARSEABLE |  | #UNPARSEABLE | 5 | Rohan Kapoor |  |  |  | Green | Sign off on Pre-UAT and final version of IAD | Not Started | 0% | 2026-08-05 | 2026-08-05 |  |  |  |  | 0 | 328 | 4 | [8 empty] | Solvara Project Manager
#UNPARSEABLE | #UNPARSEABLE | #UNPARSEABLE |  | #UNPARSEABLE | 2 | Rohan Kapoor |  |  |  | Green | Merlin Intake : Conclude Functional Configuration | Not Started | 0% | 2026-08-05 | 2026-08-05 |  |  |  |  | 0 | 329 | 4
#UNPARSEABLE | #UNPARSEABLE | #UNPARSEABLE |  | #UNPARSEABLE | 1 | Rohan Kapoor |  |  |  | Green | User Acceptance Testing (UAT) Phase II | Not Started | 0% | 2026-08-07 | 2026-08-24 |  |  |  |  | 12d |  | 34
#UNPARSEABLE | #UNPARSEABLE | #UNPARSEABLE |  | #UNPARSEABLE | 2 | Rohan Kapoor |  |  |  | Green | Prepare for UAT | Not Started | 0% | 2026-08-07 | 2026-08-12 |  |  |  |  | 4d |  | 42
#UNPARSEABLE | #UNPARSEABLE | #UNPARSEABLE |  | #UNPARSEABLE | 3 | Rohan Kapoor |  |  |  | Green | Prepare the UAT Approach | Not Started | 0% | 2026-08-07 | 2026-08-07 |  |  |  |  | 1d | 317, 330 | 0 | TRUE | [7 empty] | Zycus Product Specialist, Zycus Project Manager
#UNPARSEABLE | #UNPARSEABLE | #UNPARSEABLE |  | #UNPARSEABLE | 3 | Rohan Kapoor |  |  |  | Green | Finalize and agree on UAT Approach | Not Started | 0% | 2026-08-10 | 2026-08-10 |  |  |  |  | 1d | 333 | 0 | TRUE | [7 empty] | Solvara Core Project Team, Solvara Project Manager
#UNPARSEABLE | #UNPARSEABLE | #UNPARSEABLE |  | #UNPARSEABLE | 3 | Rohan Kapoor |  |  |  | Green | Provide users & roles on STAGING required for UAT | Not Started | 0% | 2026-08-10 | 2026-08-10 |  |  |  |  | 1d | 333 | 43 | [8 empty] | Solvara Project Manager, Solvara Project Team, Solvara SME
#UNPARSEABLE | #UNPARSEABLE | #UNPARSEABLE |  | #UNPARSEABLE | 3 | Rohan Kapoor |  |  |  | Green | Create users on STAGING set for UAT group | Not Started | 0% | 2026-08-11 | 2026-08-11 |  |  |  |  | 1d | 335 | 43 | [8 empty] | Zycus Product Specialist
#UNPARSEABLE | #UNPARSEABLE | #UNPARSEABLE |  | #UNPARSEABLE | 3 | Rohan Kapoor |  |  |  | Green | Provide Standard Test Cases | Not Started | 0% | 2026-08-11 | 2026-08-11 |  |  |  |  | 1d | 334 | 0 | TRUE | [7 empty] | Zycus Consultant, Zycus Product Specialist
#UNPARSEABLE | #UNPARSEABLE | #UNPARSEABLE |  | #UNPARSEABLE | 3 | Rohan Kapoor |  |  |  | Green | Finalize Test Cases | Not Started | 0% | 2026-08-12 | 2026-08-12 |  |  |  |  | 1d | 337 | 0 | TRUE | [7 empty] | Solvara Core Project Team
#UNPARSEABLE | #UNPARSEABLE | #UNPARSEABLE |  | #UNPARSEABLE | 3 | Rohan Kapoor |  |  |  | Green | Quality Reviews | Not Started | 0% | 2026-08-07 | 2026-08-10 |  |  |  |  | 2d |  | 44
#UNPARSEABLE | #UNPARSEABLE | #UNPARSEABLE |  | #UNPARSEABLE | 4 | Rohan Kapoor |  |  |  | Green | Schedule for quality check | Not Started | 0% | 2026-08-07 | 2026-08-07 |  |  |  |  | 1d | 178, 240, 261, 318, 330, 283 | 23 | [8 empty] | Zycus Product Specialist
#UNPARSEABLE | #UNPARSEABLE | #UNPARSEABLE |  | #UNPARSEABLE | 4 | Rohan Kapoor |  |  |  | Green | Perform quality checks, PSRs as per quality checklist and submit to QC team | Not Started | 0% | 2026-08-10 | 2026-08-10 |  |  |  |  | 1d | 340 | 23 | [8 empty] | Zycus Product Specialist
#UNPARSEABLE | #UNPARSEABLE | #UNPARSEABLE |  | #UNPARSEABLE | 4 | Rohan Kapoor |  |  |  | Green | Quality Check by Zycus QC team | Not Started | 0% | 2026-08-10 | 2026-08-10 |  |  |  |  | 0 | 341 | 21 | [8 empty] | Zycus Quality Team
#UNPARSEABLE | #UNPARSEABLE | #UNPARSEABLE |  | #UNPARSEABLE | 2 | Rohan Kapoor |  |  |  | Green | End-to-End UAT | Not Started | 0% | 2026-08-11 | 2026-08-24 |  |  |  |  | 10d |  | 34
#UNPARSEABLE | #UNPARSEABLE | #UNPARSEABLE |  | #UNPARSEABLE | 3 | Rohan Kapoor |  |  |  | Green | UAT Intake and iSource | Not Started | 0% | 2026-08-13 | 2026-08-17 |  |  |  |  | 3d | 317, 330, 338 | 0 | TRUE | [7 empty] | Solvara Core Project Team
#UNPARSEABLE | #UNPARSEABLE | #UNPARSEABLE |  | #UNPARSEABLE | 3 | Rohan Kapoor |  |  |  | Green | Defect Analysis & UAT Feedback incorporation and share Test Closure Memo | Not Started | 0% | 2026-08-14 | 2026-08-18 |  |  |  |  | 3d | 344SS +1d | 0 | TRUE | [7 empty] | Zycus Project Team
#UNPARSEABLE | #UNPARSEABLE | #UNPARSEABLE |  | #UNPARSEABLE | 3 | Rohan Kapoor |  |  |  | Green | Solvara to provide sign off on Test Closure Memo | Not Started | 0% | 2026-08-19 | 2026-08-20 |  |  |  |  | 2d | 345 | 0 | TRUE | [7 empty] | Solvara Core Project Team, Solvara Project Manager
#UNPARSEABLE | #UNPARSEABLE | #UNPARSEABLE |  | #UNPARSEABLE | 3 | Rohan Kapoor |  |  |  | Green | UAT iSupplier, eProc, eInvoice and CLM | Not Started | 0% | 2026-08-11 | 2026-08-19 |  |  |  |  | 7d | 240, 261, 177, 342 | 18 | [8 empty] | Solvara Core Project Team
#UNPARSEABLE | #UNPARSEABLE | #UNPARSEABLE |  | #UNPARSEABLE | 3 | Rohan Kapoor |  |  |  | Green | Defect Analysis & UAT Feedback incorporation and share Test Closure Memo | Not Started | 0% | 2026-08-12 | 2026-08-20 |  |  |  |  | 7d | 347SS +1d | 24 | [8 empty] | Zycus Project Team
#UNPARSEABLE | #UNPARSEABLE | #UNPARSEABLE |  | #UNPARSEABLE | 3 | Rohan Kapoor |  |  |  | Green | Solvara to provide sign off on Test Closure Memo | Not Started | 0% | 2026-08-21 | 2026-08-24 |  |  |  |  | 2d | 348 | 24 | [8 empty] | Solvara Core Project Team, Solvara Project Manager
#UNPARSEABLE | #UNPARSEABLE | #UNPARSEABLE |  | #UNPARSEABLE | 1 | Rohan Kapoor |  |  |  | Green | UAT Completion | Not Started | 0% | 2026-08-24 | 2026-08-24 |  |  |  |  | 0 | 346, 349 | 24
#UNPARSEABLE | #UNPARSEABLE | #UNPARSEABLE |  | #UNPARSEABLE | 1 | Rohan Kapoor |  |  |  | Green | Value KPI Sign-off | Not Started | 0% | 2026-07-28 | 2026-07-28 |  |  |  |  | 0 | 306 | 51 | [8 empty] | Solvara Project Group, Zycus Product Specialist, Zycus Project Manager
#UNPARSEABLE | #UNPARSEABLE | #UNPARSEABLE |  | #UNPARSEABLE | 1 | Rohan Kapoor |  |  |  | Green | Training Phase II | Not Started | 0% | 2026-08-18 | 2026-09-02 |  |  |  |  | 12d |  | 27
#UNPARSEABLE | #UNPARSEABLE | #UNPARSEABLE |  | #UNPARSEABLE | 2 | Rohan Kapoor |  |  |  | Green | Training Preparation | Not Started | 0% | 2026-08-18 | 2026-08-19 |  |  |  |  | 2d |  | 37
#UNPARSEABLE | #UNPARSEABLE | #UNPARSEABLE |  | #UNPARSEABLE | 3 | Rohan Kapoor |  |  |  | Green | Training Approach and Schedule finalization | Not Started | 0% | 2026-08-18 | 2026-08-18 |  |  |  |  | 1d | 344 | 35 | [8 empty] | Solvara Project Manager, Zycus Project Manager, Zycus University
#UNPARSEABLE | #UNPARSEABLE | #UNPARSEABLE |  | #UNPARSEABLE | 3 | Rohan Kapoor |  |  |  | Green | Training Agenda Finalization | Not Started | 0% | 2026-08-19 | 2026-08-19 |  |  |  |  | 1d | 354 | 35 | [8 empty] | Solvara Project Manager, Zycus University Trainer
#UNPARSEABLE | #UNPARSEABLE | #UNPARSEABLE |  | #UNPARSEABLE | 2 | Rohan Kapoor |  |  |  | Green | Train The Trainer | Not Started | 0% | 2026-08-21 | 2026-09-02 |  |  |  |  | 9d |  | 27
#UNPARSEABLE | #UNPARSEABLE | #UNPARSEABLE |  | #UNPARSEABLE | 3 | Rohan Kapoor |  |  |  | Green | iContract + Merlin for Contract Training | Not Started | 0% | 2026-08-25 | 2026-08-26 |  |  |  |  | 2d | 349 | 27 | [8 empty] | Solvara Project Team, Zycus University Trainer
#UNPARSEABLE | #UNPARSEABLE | #UNPARSEABLE |  | #UNPARSEABLE | 3 | Rohan Kapoor |  |  |  | Green | iSource Training | Not Started | 0% | 2026-08-21 | 2026-08-21 |  |  |  |  | 1d | 346, 355 | 34 | [8 empty] | Solvara Project Team, Zycus University Trainer
#UNPARSEABLE | #UNPARSEABLE | #UNPARSEABLE |  | #UNPARSEABLE | 3 | Rohan Kapoor |  |  |  | Green | eProc Training | Not Started | 0% | 2026-08-27 | 2026-08-28 |  |  |  |  | 2d | 357 | 27 | [8 empty] | Solvara Project Team, Zycus University Trainer
#UNPARSEABLE | #UNPARSEABLE | #UNPARSEABLE |  | #UNPARSEABLE | 3 | Rohan Kapoor |  |  |  | Green | eInvoice and Merlin APSD Training | Not Started | 0% | 2026-08-31 | 2026-08-31 |  |  |  |  | 1d | 359 | 27 | [8 empty] | Solvara Project Team, Zycus University Trainer
#UNPARSEABLE | #UNPARSEABLE | #UNPARSEABLE |  | #UNPARSEABLE | 3 | Rohan Kapoor |  |  |  | Green | Merlin Intake | Not Started | 0% | 2026-08-24 | 2026-08-24 |  |  |  |  | 1d | 358 | 34 | [8 empty] | Solvara Project Team, Zycus University Trainer
#UNPARSEABLE | #UNPARSEABLE | #UNPARSEABLE |  | #UNPARSEABLE | 3 | Rohan Kapoor |  |  |  | Green | Admin Training | Not Started | 0% | 2026-09-01 | 2026-09-02 |  |  |  |  | 2d | 360 | 27 | [8 empty] | Solvara Project Team, Zycus University Trainer
#UNPARSEABLE | #UNPARSEABLE | #UNPARSEABLE |  | #UNPARSEABLE | 1 | Rohan Kapoor |  |  |  | Green | Training Completion | Not Started | 0% | 2026-09-02 | 2026-09-02 |  |  |  |  | 0 | 362 | 27
#UNPARSEABLE | #UNPARSEABLE | #UNPARSEABLE |  | #UNPARSEABLE | 1 | Rohan Kapoor |  |  |  | Green | Production Migration Phase II | Not Started | 0% | 2026-08-21 | 2026-09-07 |  |  |  |  | 12d |  | 24
#UNPARSEABLE | #UNPARSEABLE | #UNPARSEABLE |  | #UNPARSEABLE | 2 | Rohan Kapoor |  |  |  | Green | Migration of Solution from STAGING Environment to PRODUCTION | Not Started | 0% | 2026-08-21 | 2026-09-07 |  |  |  |  | 12d |  | 24
#UNPARSEABLE | #UNPARSEABLE | #UNPARSEABLE |  | #UNPARSEABLE | 3 | Rohan Kapoor |  |  |  | Green | Configuration migration to PRODUCTION - iSource and Merlin Intake | Not Started | 0% | 2026-08-21 | 2026-08-25 |  |  |  |  | 3d | 346 | 33 | [8 empty] | Zycus Product Specialist
#UNPARSEABLE | #UNPARSEABLE | #UNPARSEABLE |  | #UNPARSEABLE | 3 | Rohan Kapoor |  |  |  | Green | Configuration migration to PRODUCTION - iSupplier, eProc, eInvoice and CLM | Not Started | 0% | 2026-08-25 | 2026-08-31 |  |  |  |  | 5d | 350 | 24 | [8 empty] | Zycus Product Specialist
#UNPARSEABLE | #UNPARSEABLE | #UNPARSEABLE |  | #UNPARSEABLE | 3 | Rohan Kapoor |  |  |  | Green | Provide the final list of users to be created on PRODUCTION | Not Started | 0% | 2026-08-21 | 2026-08-24 |  |  |  |  | 2d | 346 | 0 | TRUE | [7 empty] | Solvara Holdings SME, Solvara Project Manager, TKC Holdings Project Team
#UNPARSEABLE | #UNPARSEABLE | #UNPARSEABLE |  | #UNPARSEABLE | 3 | Rohan Kapoor |  |  |  | Green | Creation of Specified Users as per roles | Not Started | 0% | 2026-08-25 | 2026-08-28 |  |  |  |  | 4d | 368 | 0 | TRUE | [7 empty] | Zycus Product Specialist
#UNPARSEABLE | #UNPARSEABLE | #UNPARSEABLE |  | #UNPARSEABLE | 3 | Rohan Kapoor |  |  |  | Green | Migrate integration code to Prod | Not Started | 0% | 2026-09-01 | 2026-09-07 |  |  |  |  | 5d | 346, 349, 367 | 24 | [8 empty] | Solvara Integration Team
#UNPARSEABLE | #UNPARSEABLE | #UNPARSEABLE |  | #UNPARSEABLE | 3 | Rohan Kapoor |  |  |  | Green | Quality Reviews | Not Started | 0% | 2026-08-31 | 2026-09-01 |  |  |  |  | 2d |  | 28
#UNPARSEABLE | #UNPARSEABLE | #UNPARSEABLE |  | #UNPARSEABLE | 4 | Rohan Kapoor |  |  |  | Green | Schedule for quality check | Not Started | 0% | 2026-08-31 | 2026-08-31 |  |  |  |  | 1d | 369 | 0 | TRUE | [7 empty] | Zycus Product Specialist
#UNPARSEABLE | #UNPARSEABLE | #UNPARSEABLE |  | #UNPARSEABLE | 4 | Rohan Kapoor |  |  |  | Green | Perform quality checks, PSRs as per quality checklist and submit to QC team | Not Started | 0% | 2026-09-01 | 2026-09-01 |  |  |  |  | 1d | 372 | 0 | TRUE | [7 empty] | Zycus Product Specialist
#UNPARSEABLE | #UNPARSEABLE | #UNPARSEABLE |  | #UNPARSEABLE | 4 | Rohan Kapoor |  |  |  | Green | Quality Check by Zycus QC team | Not Started | 0% | 2026-09-01 | 2026-09-01 |  |  |  |  | 0 | 373 | 0 | TRUE | [7 empty] | Zycus Quality Team
#UNPARSEABLE | #UNPARSEABLE | #UNPARSEABLE |  | #UNPARSEABLE | 1 | Rohan Kapoor |  |  |  | Green | Sanity on Production - iSource and Merlin Intake | Not Started | 0% | 2026-09-02 | 2026-09-02 |  |  |  |  | 1d | 374 | 25 | [8 empty] | Solvara IT Team, Solvara Integration Team, Solvara Project Manager, Solvara SME, Solvara Subject Matter Expert
#UNPARSEABLE | #UNPARSEABLE | #UNPARSEABLE |  | #UNPARSEABLE | 1 | Rohan Kapoor |  |  |  | Green | Go /No-go Check Point ( Meeting with Solvara) - iSource and Merlin Intake | Not Started | 0% | 2026-09-03 | 2026-09-03 |  |  |  |  | 1d | 375 | 25 | [8 empty] | Solvara Project Manager
#UNPARSEABLE | #UNPARSEABLE | #UNPARSEABLE |  | #UNPARSEABLE | 1 | Rohan Kapoor |  |  |  | Green | Release Zycus system to all users - iSource and Merlin Intake | Not Started | 0% | 2026-09-04 | 2026-09-04 |  |  |  |  | 1d | 376 | 25 | [8 empty] | Zycus Product Specialist
#UNPARSEABLE | #UNPARSEABLE | #UNPARSEABLE |  | #UNPARSEABLE | 1 | Rohan Kapoor |  |  |  | Green | KPI Reports to be migrated on PROD | Not Started | 0% | 2026-09-01 | 2026-09-02 |  |  |  |  | 2d | 351, 367 | 27 | [8 empty] | Solvara Project Group, Zycus Product Specialist, Zycus Project Manager
#UNPARSEABLE | #UNPARSEABLE | #UNPARSEABLE |  | #UNPARSEABLE | 1 | Rohan Kapoor |  |  |  | Green | Sanity on Production - iSupplier, eProc, eInvoice and CLM | Not Started | 0% | 2026-09-08 | 2026-09-09 |  |  |  |  | 2d | 374FS +4d | 0 | TRUE | [7 empty] | Solvara IT Team, Solvara Integration Team, Solvara Project Manager, Solvara SME, Solvara Subject Matter Expert
#UNPARSEABLE | #UNPARSEABLE | #UNPARSEABLE |  | #UNPARSEABLE | 1 | Rohan Kapoor |  |  |  | Green | Go /No-go Check Point ( Meeting with Solvara) - iSupplier, eProc, eInvoice and CLM | Not Started | 0% | 2026-09-10 | 2026-09-10 |  |  |  |  | 1d | 379 | 0 | TRUE | [7 empty] | Solvara Project Manager
#UNPARSEABLE | #UNPARSEABLE | #UNPARSEABLE |  | #UNPARSEABLE | 1 | Rohan Kapoor |  |  |  | Green | Release Zycus system to all users - iSupplier, eProc, eInvoice and CLM | Not Started | 0% | 2026-09-11 | 2026-09-11 |  |  |  |  | 1d | 380 | 0 | TRUE | [7 empty] | Zycus Product Specialist
#UNPARSEABLE | #UNPARSEABLE | #UNPARSEABLE |  | #UNPARSEABLE | 1 | Rohan Kapoor |  |  |  | Green | Production Go-Live Phase II | Not Started | 0% | 2026-09-11 | 2026-09-11 |  |  |  |  | 0 | 381 | 0 | TRUE
#UNPARSEABLE | #UNPARSEABLE | #UNPARSEABLE |  | #UNPARSEABLE | 1 | Rohan Kapoor |  |  |  | Green | Hypercare Phase II | Not Started | 0% | 2026-09-14 | 2026-10-09 |  |  |  |  | 20d | 382 | 0 | TRUE | [7 empty] | Solvara IT Team, Solvara Integration Team, Solvara Project Group, Zycus Consultant, Zycus Integration Team, Zycus Product Specialist, Zycus Project Manager

## Summary
Project Name
Project Manager | Rohan Kapoor
Project Start Date | 2026-02-11
Project End Date | 2026-10-09
Not Started | 175
In Progress | 35
Completed | 133
On Hold | 0
At Risk | High
Project Stage | Training Phase I
% Complete | 44%
Schedule Health | Red
Today's Date | 2026-07-02
Target Start Date | #UNPARSEABLE
Target End Date | #UNPARSEABLE
Schedule Delta | #UNPARSEABLE
Duration | 170
Target Dates Variance | #UNPARSEABLE
Schedule Variance | #UNPARSEABLE
Project Status | In Progress